## FORGING PRIORITY 64s (hidden)
Forging Plan | [10 empty] | DOC NO:
REV NO:
M/C NAME: 64S (T01) | [5 empty] | FROM | 2024-03-06 |  |  |  | REV DATE:
[6 empty] | TO | 2024-06-10 |  |  |  | ISSUE DATE | 2024-03-06
S.no | Part no | Part Name | Grade | Customer | Mat. Grade / SIZE | Quantity | Weight | W.O Date | Process Completion Date | Dispatch Date | status/priority | Remarks
1 | S006010581 | M6X1X10 HHS | PPL-A2-70 | internal stock | 304/5.20 | 20000 | 840 | 2024-03-06 |  |  | 1
2 | S006020581 | M6X1X20 HHS | GTI-A270 | internal stock | 304/5.20 | 100000 | 5300 |  |  |  | 2
3 | LAC00010 | M6X1X15 LSHCB | PPL-A 800 | internal stock | 304/5.20 | 15000 | 180
4 | NPD | M6X1X18 HHS | PPL-9.8 | internal stock | 15B25/5.75 | 2000 | 32
5 | U006020981 | M6X1X20 SHCS | PPL-A800 | internal stock | 204/5.20 | 5000 | 315
6 | U006025981 | M6X1X25 SHCS | PPL-A800 | internal stock | 204/5.20 | 5000 | 357.5
7 | U006016581 | M6X1X16 SHCS | PPL-A270 | internal stock | 304/5.20 | 100000 | 575
8 | U006012781 | M6X1X12SHCS | PPL-A470 | internal stock | 316/5.20 | 20000 | 160
TOTAL | [5 empty] | 267000 | 7759.5
| M/C SPEED | OUTPUT/DAY IN 75% | AVAILABLE TIME OF THIS MONTH PRODUCTION {75%) | PLAN OF PRODUCTION/THIS MONTH | NO.DAYS REQUIRED BASED ON 75% OUTPUT
| 100PIECE/MINS | 40500 | 1053000 | 267000 | 6.5926
PREPARED BY: APPROVED BY:
NOTE: | PRIORITY OF ITEMS BASED ON THE CUSTOMER URGENCY & NPDS

## FORGING PRIORITY 6L4 (hidden)
Forging Plan | [10 empty] | DOC NO:
REV NO:
M/C NAME: 6L4 (T03) | [5 empty] | FROM | 2024-03-06 |  |  |  | REV DATE:
[6 empty] | TO | 2024-06-10 |  |  |  | ISSUE DATE | 2024-03-06
S.no | Part no | Part Name | Grade | Customer | Mat. Grade / SIZE | Quantity | Weight | W.O Date | Process Completion Date | Dispatch Date | status/priority | Remarks
1 | L010025201 | M10X1.5X25 HHS 16A/F | PPL-10.9 | INTERNAL | 10B35/9.7 | 5000 | 120
2 | L010025401 | M10X1.5X25 HHS 16A/F | PPL-8.8 | INTERNAL | 10B35/9.7 | 8000 | 181.6
3 | L010030401 | M10X1.5X30 HHS 16A/F | PPL-8.8 | INTERNAL | 10B35/9.7 | 5000 | 120
4 | L010035401 | M10X1.5X35 HHS 16A/F | PPL-8.8 | INTERNAL | 10B35/9.7 | 25000 | 750
5 | L010040401 | M10X1.5X40 HHS 16A/F | PPL-8.8 | INTERNAL | 10B35/9.7 | 2500 | 87.5
6 | L010045401 | M10X1.5X45 HHS 16A/F | PPL-8.8 | INTERNAL | 10B35/9.7 | 4500 | 171
7 | L010050401 | M10X1.5X50 HHS 16A/F | PPL-8.8 | INTERNAL | 10B35/9.7 | 25000 | 995
8 | L010055401 | M10X1.5X55 HHS 16A/F | PPL-8.8 | INTERNAL | 10B35/9.7 | 12000 | 528
9 | L010065401 | M10X1.5X65 HHS 16A/F | PPL-8.8 | INTERNAL | 10B35/9.7 | 500 | 24.5
10 | L010020203 | M10X1.5X20 HHS 17A/F | PPL-10.9 | INTERNAL | 10B35/9.7 | 5000 | 120
11 | L010025203 | M10X1.5X25 HHS 17A/F | PPL-10.9 | INTERNAL | 10B35/9.7 | 10000 | 280
12 | L010035203 | M10X1.5X35 HHS 17A/F | PPL-10.9 | INTERNAL | 10B35/9.7 | 6000 | 192
13 | L010035204 | M10X1.5X35 HHB 17 A/F | PPL-10.9 | INTERNAL | 10B35/9.7 | 20000 | 640
14 | L010040204 | M10X1.5X40 HHB 17 A/F | PPL-10.9 | INTERNAL | 10B35/9.7 | 6000 | 210
15 | L010050204 | M10X1.5X50 HHB 17 A/F | PPL-10.9 | INTERNAL | 10B35/9.7 | 10000 | 420
16 | L010065204 | M10X1.5X65 HHB 17 A/F | PPL-10.9 | INTERNAL | 10B35/9.7 | 10000 | 500
17 | L010070204 | M10X1.5X70 HHB 17 A/F | PPL-10.9 | INTERNAL | 10B35/9.7 | 3000 | 159
18 | L010065402 | M10X1.5X65 HHB 16A/F | PPL-8.8 | INTERNAL | 10B35/9.7 | 2400 | 120
19 | L010070402 | M10X1.5X70 HHB 16A/F | PPL-8.8 | INTERNAL | 10B35/9.7 | 2400 | 127.2
20 | A010025401 | M10X1.5X25 SHCS | PPL-8.8 | INTERNAL | 10B35/9.7 | 4000 | 100
21 | A010030401 | M10X1.5X30 SHCS | PPL-8.8 | INTERNAL | 10B35/9.7 | 6000 | 162
22 | A010040401 | M10X1.5X40 SHCS | PPL-8.8 | INTERNAL | 10B35/9.7 | 7000 | 224
23 | A010030201 | M10X1.5X30 SHCS | PPL-12.9 | INTERNAL | 4140/9.7 | 5000 | 135
24 | V010030201 | M10X1.5X35 SPL 14A/F | PPL-10.9 | INTERNAL | 10B35/9.7 | 5000 | 125
TOTAL | [5 empty] | 189300 | 3590.8
| M/C SPEED | OUTPUT/DAY IN 75% | AVAILABLE TIME OF THIS MONTH PRODUCTION {75%) | PLAN OF PRODUCTION/THIS MONTH | NO.DAYS REQUIRED BASED ON 75% OUTPUT
| 100PIECE/MINS | 40500 | 1053000 | 189300 | 4.6741
PREPARED BY: APPROVED BY:
NOTE: | PRIORITY OF ITEMS BASED ON THE CUSTOMER URGENCY & NPDS

## FORGING PRIORITY 6L4 (2) (hidden)
Forging Plan | [10 empty] | DOC NO:
REV NO:
M/C NAME: 64S (T01) | [5 empty] | FROM | 2024-03-06 |  |  |  | REV DATE:
[6 empty] | TO | 2024-03-10 |  |  |  | ISSUE DATE | 2023-01-05
S.no | Part no | Part Name | Grade | Customer | Mat. Grade / SIZE | Quantity | Weight | W.O Date | Process Completion Date | Dispatch Date | status/priority | Remarks
1 | L016065402 | M16X2X65 HHB | PPL-8.8 | SCKL | 10B35/15.65 | 11000 | 1405.8 | 2024-03-06 | 2024-03-06
2 | L016070402 | M16X2X70 HHB | PPL-8.8 | SCKL | 10B35/15.65 | 2500 | 338
3 | L016090402 | M16X2X90 HHB | PPL-8.8 | SCKL | 10B35/15.65 | 350 | 58.1
4 | L016100402 | M16X2X100 HHB | PPL-8.8 | SCKL | 10B35/15.65 | 250 | 45.25
5 | L012050402 | M12X1.75X50 HHB 18A/F | PPL-8.8 | SCKL | 10B35/11.60 | 12000 | 612
6 | L012060402 | M12X1.75X60 HHB 18A/F | PPL-8.8 | SCKL | 10B35/11.60 | 3500 | 217
7 | L012070202 | M12X1.75X70 HHB 18A/F | PPL-10.9 | BEML | 10B35/11.60 | 1500 | 106.5
8 | L012110202 | M12X1.75X110 HHB 18A/F | PPL-10.9 | BEML | 10B35/11.60 | 500 | 55
9 | L012030401 | M12X1.75X30 HHS 18A/F | PPL-8.8 | AKAY | 10B35/11.60 | 6000 | 222
10 | L012050401 | M12X1.75X50 HHS 18A/F | PPL-8.8 | AKAY | 10B35/11.60 | 21000 | 1071
11 | L012040201 | M12X1.75X40 HHS 18A/F | PPL-10.9 | BEML | 10B35/11.60 | 4000 | 176
12 | L112030203 | M12X1.5X30 HHS 19A/F | PPL-10.9 | AUTO | 10B35/11.60 | 4000 | 148
13 | L112035203 | M12X1.5X35 HHS 19A/F | PPL-10.9 | AUTO | 10B35/11.60 | 6000 | 252
14 | L112045203 | M12X1.5X45 HHS 19A/F | PPL-10.9 | AUTO | 10B35/11.60 | 2000 | 96
15 | L012045203 | M12X1.75X45 HHS 19A/F | PPL-10.9 | AUTO | 10B35/11.60 | 2000 | 100
16 | L012050203 | M12X1.75X50 HHS 19A/F | PPL-10.9 | AUTO | 10B35/11.60 | 2000 | 104
TOTAL | [5 empty] | 78600 | 5006.65
| M/C SPEED | OUTPUT/DAY IN 75% | AVAILABLE TIME OF THIS MONTH PRODUCTION {75%) | PLAN OF PRODUCTION/THIS MONTH | NO.DAYS REQUIRED BASED ON 75% OUTPUT
| 100PIECE/MINS | 40500 | 1053000 | 175000 | 4.321
PREPARED BY: APPROVED BY:
NOTE: | PRIORITY OF ITEMS BASED ON THE CUSTOMER URGENCY & NPDS

## FORGING PRIORITY 254LL (hidden)
Forging Plan | [10 empty] | DOC NO:
REV NO:
M/C NAME: 254LL (T05) | [5 empty] | FROM | 2024-03-06 |  |  |  | REV DATE:
[6 empty] | TO | 2024-03-10 |  |  |  | ISSUE DATE | 2023-01-05
S.no | Part no | Part Name | Grade | Customer | Mat. Grade / SIZE | Quantity | Weight | W.O Date | Process Completion Date | Dispatch Date | status/priority | Remarks
1 | L020070402 | M20X2.5X70 HHB | PPL-8.8 | INTERNAL | 10B35/19.65 | 380 | 85.462 | 2024-03-06 | 2024-03-06
2 | L020090402 | M20X2.5X90 HHB | PPL-8.8 | INTERNAL | 10B35/19.65 | 1500 | 407.1
3 | L020140402 | M20X2.5X140 HHB | PPL-8.8 | INTERNAL | 10B35/19.65 | 1200 | 472.8
4 | L024150402 | M24X3X150 HHB | PPL-8.8 | INTERNAL | 15B41/23.60 | 100 | 624
5 | L024160402 | M24X3X160 HHB | PPL-8.8 | INTERNAL | 15B41/23.60 | 360 | 360
6 | L024100402 | M24X3X100 HHB | PPL-8.8 | INTERNAL | 15B41/23.60 | 400 | 440
7 | L024120402 | M24X3X120 HHB | PPL-8.8 | INTERNAL | 15B41/23.60 | 1000 | 654
8 | CFB0222020 | M20X2.5X120 HHB | PPL-10.9 | INTERNAL | 15B41/19.6 | 130 | 47.32
9 | CFB0122095 | M20X2.5X95 HHB | PPL-10.9 | INTERNAL | 15B41/19.6 | 2300 | 650.9
10 | CFB0122480 | M24X3X80 HHB | PPL-10.9 | INTERNAL | 15B41/23.60 | 1766 | 653.42
11 | CFB0222475 | M24X3X175 HHB | PPL-10.9 | INTERNAL | 15B41/23.60 | 3096 | 2167.2
12 | CFB0222445 | M24X3X145 HHB | PPL-10.9 | INTERNAL | 15B41/23.60 | 765 | 459
13 | CFS0132470 | M24X3X70 HHS | PPL-10.9 | INTERNAL | 15B41/23.60 | 3410 | 1125.3
14 | CFS0132460 | M24X3X60 HHS | PPL-10.9 | INTERNAL | 15B41/23.60 | 3500 | 1050
15 | CFB0222400 | M24X3X100 HHB | PPL-10.9 | INTERNAL | 15B41/23.60 | 938 | 413.658
16 | CFB0722790 | M27X3X90 HHB | PPL-10.9 | INTERNAL | 15B41/26.6 | 200 | 120
TOTAL | [5 empty] | 21045 | 9730.16
| M/C SPEED | OUTPUT/DAY IN 75% | AVAILABLE TIME OF THIS MONTH PRODUCTION {75%) | PLAN OF PRODUCTION/THIS MONTH | NO.DAYS REQUIRED BASED ON 75% OUTPUT
| 40PIECE/MINS | 16200 | 421200 | 21045 | 1.2991
PREPARED BY: APPROVED BY:
NOTE: | PRIORITY OF ITEMS BASED ON THE CUSTOMER URGENCY & NPDS

## FORGING PRIORITY 164 S (hidden)
Forging Plan | [14 empty] | DOC NO:
REV NO:
M/C NAME: 64S (T01) | [9 empty] | FROM | 2024-03-06 |  |  |  | REV DATE:
[10 empty] | TO | 2024-03-10 |  |  |  | ISSUE DATE | 2023-01-05
S.no | Part no | Part Name | Size | Length | Pitch | A/F | Grade | Customer | Mat. Grade / SIZE | Quantity | Weight | W.O Date | Process Completion Date | Dispatch Date | status/priority | Remarks
1 | L016065402 | M16X2X65 HHB | 16 | 65 | 2 | 24 | PPL-8.8 | INTERNAL | 10B35/15.65 | 11000 | 1405.8 | 2024-03-06 | 2024-03-06
2 | L016070402 | M16X2X70 HHB | 16 | 70 | 2 | 24 | PPL-8.8 | INTERNAL | 10B35/15.65 | 2500 | 338
3 | L016090402 | M16X2X90 HHB | 16 | 90 | 2 | 24 | PPL-8.8 | INTERNAL | 10B35/15.65 | 350 | 58.1
4 | L016100402 | M16X2X100 HHB | 16 | 100 | 2 | 24 | PPL-8.8 | INTERNAL | 10B35/15.65 | 250 | 45.25
5 | L012050402 | M12X1.75X50 HHB 18A/F | 12 | 50 | 1.75 | 18 | PPL-8.8 | INTERNAL | 10B35/11.60 | 12000 | 612
6 | L012060402 | M12X1.75X60 HHB 18A/F | 12 | 60 | 1.75 | 18 | PPL-8.8 | INTERNAL | 10B35/11.60 | 3500 | 217
7 | L012070202 | M12X1.75X70 HHB 18A/F | 12 | 70 | 1.75 | 18 | PPL-10.9 | INTERNAL | 10B35/11.60 | 1500 | 106.5
8 | L012110202 | M12X1.75X110 HHB 18A/F | 12 | 110 | 1.75 | 18 | PPL-10.9 | INTERNAL | 10B35/11.60 | 500 | 55
9 | L012030401 | M12X1.75X30 HHS 18A/F | 12 | 30 | 1.75 | 18 | PPL-8.8 | INTERNAL | 10B35/11.60 | 8000 | 296
10 | L012050401 | M12X1.75X50 HHS 18A/F | 12 | 50 | 1.75 | 18 | PPL-8.8 | INTERNAL | 10B35/11.60 | 21000 | 1071
11 | L012040401 | M12X1.75X40 HHS 18A/F | 12 | 40 | 1.75 | 18 | PPL-8.8 | INTERNAL | 10B35/11.60 | 3000 | 132
12 | L012055401 | M12X1.75X55 HHS 18A/F | 12 | 55 | 1.75 | 18 | PPL-8.8 | INTERNAL | 10B35/11.60 | 1200 | 52.8
11 | L012040201 | M12X1.75X40 HHS 18A/F | 12 | 40 | 1.75 | 18 | PPL-10.9 | INTERNAL | 10B35/11.60 | 4000 | 176
12 | L112030203 | M12X1.5X30 HHS 19A/F | 12 | 30 | 1.5 | 19 | PPL-10.9 | INTERNAL | 10B35/11.60 | 4000 | 148
13 | L112035203 | M12X1.5X35 HHS 19A/F | 12 | 35 | 1.5 | 19 | PPL-10.9 | INTERNAL | 10B35/11.60 | 6000 | 252
14 | L112045203 | M12X1.5X45 HHS 19A/F | 12 | 45 | 1.5 | 19 | PPL-10.9 | INTERNAL | 10B35/11.60 | 2000 | 96
15 | L012045203 | M12X1.75X45 HHS 19A/F | 12 | 45 | 1.75 | 19 | PPL-10.9 | INTERNAL | 10B35/11.60 | 2000 | 100
16 | L012050203 | M12X1.75X50 HHS 19A/F | 12 | 50 | 1.75 | 19 | PPL-10.9 | INTERNAL | 10B35/11.60 | 2000 | 104
17 | V114035204 | M14X1.5X35 HHB 22A/F | 14 | 35 | 1.5 | 22 | PPL-10.9 | INTERNAL | 10B35/13.65 | 5000 | 323.5
18 | V114040204 | M14X1.5X40 HHB 22A/F | 14 | 40 | 1.5 | 22 | PPL-10.9 | INTERNAL | 10B35/13.65 | 20000 | 1384
19 | L114045204 | M14X1.5X45 HHB 22A/F | 14 | 45 | 1.5 | 22 | PPL-10.9 | INTERNAL | 10B35/13.65 | 3000 | 224.4
20 | L114050204 | M14X1.5X50 HHB 22A/F | 14 | 50 | 1.5 | 22 | PPL-10.9 | INTERNAL | 10B35/13.65 | 3000 | 239.4
21 | L114060204 | M14X1.5X60 HHB 22A/F | 14 | 60 | 1.5 | 22 | PPL-10.9 | INTERNAL | 10B35/13.65 | 3500 | 319.2
22 | L114065204 | M14X1.5X65 HHB 22A/F | 14 | 65 | 1.5 | 22 | PPL-10.9 | INTERNAL | 10B35/13.65 | 3000 | 292.8
23 | L114070204 | M14X1.5X70 HHB 22A/F | 14 | 70 | 1.5 | 22 | PPL-10.9 | INTERNAL | 10B35/13.65 | 2000 | 206.8
24 | L114075204 | M14X1.5X75 HHB 22A/F | 14 | 75 | 1.5 | 22 | PPL-10.9 | INTERNAL | 10B35/13.65 | 3000 | 327.6
25 | L014050204 | M14X2X50 HHB 22A/F | 14 | 50 | 2 | 22 | PPL-10.9 | INTERNAL | 10B35/13.65 | 2000 | 159.6
26 | L014060204 | M14X2X60 HHB 22A/F | 14 | 60 | 2 | 22 | PPL-10.9 | INTERNAL | 10B35/13.65 | 2000 | 178
27 | L014065204 | M14X2X65 HHB 22A/F | 14 | 65 | 2 | 22 | PPL-10.9 | INTERNAL | 10B35/13.65 | 1200 | 114.24
28 | CFB0721425 | M14X2X25 HHS 21A/F | 14 | 25 | 2 | 21 | PPL-10.9 | INTERNAL | 10B35/13.65 | 1000 | 25
29 | CFB0721440 | M14X2X40 HHB 21 A/F | 14 | 40 | 2 | 21 | PPL-10.9 | INTERNAL | 10B35/13.65 | 2000 | 600
30 | CFB0821410 | M14X2X110 HHB 21 A/F | 14 | 110 | 2 | 21 | PPL-10.9 | INTERNAL | 10B35/13.65 | 200 | 29.4
31 | CFB1751440 | M14X1.5X40 HHB 21A/F | 14 | 40 | 1.5 | 21 | PPL-10.9 | INTERNAL | 10B35/13.65 | 5000 | 345
32 | CFS1321455 | M14X2X55 SHCS | 14 | 55 | 2 |  | PPL-12.9 | INTERNAL | 4140 | 700 | 57.4
33 | CFS1331435 | M14X2X35 SHCS | 14 | 35 | 2 |  | PPL-12.9 | INTERNAL | 4140 | 2000 | 126
34 | CFS1431410 | M14X2X100 SHCB | 14 | 100 | 2 |  | PPL-12.9 | INTERNAL | 4140 | 200 | 25.4
35 | L012020203 | M12X1.75X20 HHS | 12 | 20 | 1.75 | 19 | PPL-10.9 | INTERNAL | 10B35/11.60 | 1200 | 28.56
36 | L012045203 | M12X1.75X20 HHS | 12 | 45 | 1.75 | 19 | PPL-10.9 | INTERNAL | 10B35/11.60 | 1200 | 56.892
37 | L012050203 | M12X1.75X20 HHS | 12 | 50 | 1.75 | 19 | PPL-10.9 | INTERNAL | 10B35/11.60 | 2000 | 100.82
38 | V012040204 | M12X1.75X40 HHB | 12 | 40 | 1.75 | 19 | PPL-10.9 | INTERNAL | 10B35/11.60 | 2000 | 91.6
39 | L012075204 | M12X1.75X40 HHB | 12 | 75 | 1.75 | 19 | PPL-10.9 | INTERNAL | 10B35/11.60 | 2000 | 151
40 | L012090204 | M12X1.75X40 HHB | 12 | 90 | 1.75 | 19 | PPL-10.9 | INTERNAL | 10B35/11.60 | 1200 | 104.88
41 | L112030203 | M12X1.5X30 HHS | 12 | 30 | 1.5 | 19 | PPL-10.9 | INTERNAL | 10B35/11.60 | 4000 | 152
42 | L112035203 | M12X1.5X35 HHS | 12 | 35 | 1.5 | 19 | PPL-10.9 | INTERNAL | 10B35/11.60 | 6000 | 300
43 | L112045203 | M12X1.5X45 HHS | 12 | 45 | 1.5 | 19 | PPL-10.9 | INTERNAL | 10B35/11.60 | 2000 | 100
44 | L112050204 | M12X1.5X50 HHB | 12 | 50 | 1.5 | 19 | PPL-10.9 | INTERNAL | 10B35/11.60 | 5000 | 256
45 | L112060204 | M12X1.5X60 HHB | 12 | 60 | 1.5 | 19 | PPL-10.9 | INTERNAL | 10B35/11.60 | 2000 | 128
46 | L112065204 | M12X1.5X65 HHB | 12 | 65 | 1.5 | 19 | PPL-10.9 | INTERNAL | 10B35/11.60 | 2000 | 136
47 | L112075204 | M12X1.5X75 HHB | 12 | 75 | 1.5 | 19 | PPL-10.9 | INTERNAL | 10B35/11.60 | 2000 | 151.6
48 | L112100204 | M12X1.5X100 HHB | 12 | 100 | 1.5 | 19 | PPL-10.9 | INTERNAL | 10B35/11.60 | 1200 | 117.6
49 | L112120204 | M12X1.5X120 HHB | 12 | 120 | 1.5 | 19 | PPL-10.9 | INTERNAL | 10B35/11.60 | 1100 | 127.82
50 | G116033981 | M16X1.5X33 | 16 | 33 | 1.5 | 24 | PPL-A800 | INTERNAL | 204/17.40 | 40000 | 4400
51 | G110027981 | m10x1.5x27 | 10 | 27 | 1.5 | 17 | PPL-A800 | INTERNAL | 204/13.65 | 50000 | 2350
52 | G110020981 | m10x1.5x20(30) | 10 | 20 | 1.5 | 17 | PPL-A800 | INTERNAL | 204/13.65 | 12000 | 564
53 | G110020981 | m10x1.5x20(36) | 10 | 20 | 1.5 | 17 | PPL-A800 | INTERNAL | 204/13.65 | 2000 | 94
54 | G110022981 | m10x1.5x22.8 | 10 | 22 | 1.5 | 17 | PPL-A800 | INTERNAL | 204/13.65 | 60000 | 2820
55 | L016040201 | M16X2X40 HHS | 16 | 40 | 2 | 24 | PPL-10.9 | INTERNAL | 10B35/15.65 | 2400 | 213.12
56 | L016045201 | M16X2X45 HHS | 16 | 45 | 2 | 24 | PPL-10.9 | INTERNAL | 10B35/15.65 | 1200 | 114.24
57 | L016050201 | M16X2X50 HHS | 16 | 50 | 2 | 24 | PPL-10.9 | INTERNAL | 10B35/15.65 | 1200 | 121.92
58 | L016050202 | M16X2X50 HHB | 16 | 50 | 2 | 24 | PPL-10.9 | INTERNAL | 10B35/15.65 | 1200 | 121.92
59 | L116030201 | M16X1.5X30 HHS | 16 | 30 | 1.5 | 24 | PPL-10.9 | INTERNAL | 10B35/15.65 | 2600 | 174.2
60 | L116045201 | M16X1.5X45 HHS | 16 | 45 | 1.5 | 24 | PPL-10.9 | INTERNAL | 10B35/15.65 | 1200 | 117.6
61 | L116050202 | M16X1.5X50 HHB | 16 | 50 | 1.5 | 24 | PPL-10.9 | INTERNAL | 10B35/15.65 | 3000 | 319.8
62 | L116060202 | M16X1.5X60 HHB | 16 | 60 | 1.5 | 24 | PPL-10.9 | INTERNAL | 10B35/15.65 | 2000 | 242.8
63 | L116070202 | M16X1.5X70 HHB | 16 | 70 | 1.5 | 24 | PPL-10.9 | INTERNAL | 10B35/15.65 | 2000 | 273.2
64 | L116100202 | M16X1.5X100 HHB | 16 | 100 | 1.5 | 24 | PPL-10.9 | INTERNAL | 10B35/15.65 | 1200 | 219.12
65 | L116110202 | M16X1.5X110 HHB | 16 | 110 | 1.5 | 24 | PPL-10.9 | INTERNAL | 10B35/15.65 | 1200 | 235.2
66 | L116130202 | M16X1.5X130 HHB | 16 | 130 | 1.5 | 24 | PPL-10.9 | INTERNAL | 10B35/15.65 | 1000 | 227
67 | V01035 202 | M10X1.5X35 GUIDE BOLT | 10 | 35 | 1.5 | 17 | PPL-10.9 | INTERNAL | 10B35/11.60 | 5000 | 500
TOTAL | [9 empty] | 367700 | 25354.082
| M/C SPEED | OUTPUT/DAY IN 75% |  |  |  |  | AVAILABLE TIME OF THIS MONTH PRODUCTION {75%) | PLAN OF PRODUCTION/THIS MONTH | NO.DAYS REQUIRED BASED ON 75% OUTPUT
| 100PIECE/MINS | 20250 |  |  |  |  | 1053000 | 367700 | 18.158
PREPARED BY: APPROVED BY:
NOTE: | PRIORITY OF ITEMS BASED ON THE CUSTOMER URGENCY & NPDS
COMPLETED
U/ PROCESS
CRITICIAL/ ISSUES

## FORGING PRIORITY 164s (hidden)
FORGING DAILY OR WEEKLY PRIORITY | [7 empty] | Format No | DOC NO:
[8 empty] | Rev no | REV NO:
PERCI FAST PVT LTD - BETHAMCHERLA, KURNOOL (dt) 518599 | [7 empty] | Rev.Dt | REV DATE:
[8 empty] | DATE: | ISSUE DATE
s.no | Part no | Part Name | Grade | Customer | Mat. Grade / SIZE | MACHINE | Quantity | Weight | status/priority | Remarks
7 | V112035204 | M12X1.5X35 HHB | PPL-10.9-19A/F | ALL CUS. ORDER | 15B25/11.63 | 164S | 3000 |  | 7 | TOOL ISSUE
8 | V112040204 | M12X1.5X40 HHB | PPL-10.9-19A/F | ALL CUS. ORDER | 15B25/11.63 | 164S | 5000 |  | 8 | TOOL ISSUE
9 | L112050204 | M12X1.5X50 HHB | PPL-10.9-19A/F | ALL CUS. ORDER | 15B25/11.63 | 164S | 6000 |  | 9
10 | L112060204 | M12X1.5X60 HHB | PPL-10.9-19A/F | ALL CUS. ORDER | 15B25/11.63 | 164S | 1200 |  | 10
11 | L112070204 | M12X1.5X70 HHB | PPL-10.9-19A/F | ALL CUS. ORDER | 15B25/11.63 | 164S | 1200 |  | 11
12 | L012075402 | M12X1.75X75 HHB | PPL-8.8-18A/F | ALL CUS. ORDER | 15B25/11.63 | 164S | 1500 |  | 12
13 | L012080402 | M12X1.75X80 HHB | PPL-8.8-18A/F | ALL CUS. ORDER | 15B25/11.63 | 164S | 1300 |  | 13
14 | L012090402 | M12X1.75X90 HHB | PPL-8.8-18A/F | ALL CUS. ORDER | 15B25/11.63 | 164S | 2000 |  | 14
15 | V012035204 | M12X1.75X35 HHB | PPL-10.9-19A/F | ALL CUS. ORDER | 15B25/11.63 | 164S | 12000 |  | 15 | TOOL ISSUE
16 | L012045204 | M12X1.75X45 HHB | PPL-10.9-19A/F | ALL CUS. ORDER | 15B25/11.63 | 164S | 3000 |  | 16
17 | L012050204 | M12X1.75X50 HHB | PPL-10.9-19A/F | ALL CUS. ORDER | 15B25/11.63 | 164S | 2000 |  | 17
18 | L012025203 | M12X1.75X25 HHS | PPL-10.9-19A/F | ALL CUS. ORDER | 15B25/11.63 | 164S | 5000 |  | 18 | FAST MOVING FG BASED
19 | L012030203 | M12X1.75X30 HHS | PPL-10.9-19A/F | ALL CUS. ORDER | 15B25/11.63 | 164S | 5000 |  | 19 | FAST MOVING FG BASED
20 | V114035204 | M14X1.5X35 HHB | PPL-10.9-22A/F | ALL CUS. ORDER | 10B35/13.65 | 164S | 20000 |  | 20 | TOOL ISSUE
21 | V114040204 | M14X1.5X40 HHB | PPL-10.9-22A/F | ALL CUS. ORDER | 10B35/13.65 | 164S | 12000 |  | 21 | TOOL ISSUE
22 | L114065204 | M14X1.5X65 HHB | PPL-10.9-22A/F | ALL CUS. ORDER | 10B35/13.65 | 164S | 2000 |  | 22
23 | L114075204 | M14X1.5X75 HHB | PPL-10.9-22A/F | ALL CUS. ORDER | 10B35/13.65 | 164S | 3500 |  | 23
24
25
26
27
28
29
SIGN | PRODUCTION (C.F,ROLLING) HOD/INCHARGE |  | TOOL ROOM HOD/INCHARGE |  | QUALITY HOD/INCHARGE |  | PPC HOD/ INCHARGE
NOTE: | PRIORITY OF ITEMS BASED ON THE CUSTOMER URGENCY
PREPARED BY: | [6 empty] | APPROVED BY:

## FORGING PRIORITY 164s 1 (hidden)
FORGING DAILY OR WEEKLY PRIORITY | [7 empty] | Format No | DOC NO:
[8 empty] | Rev no | REV NO:
PERCI FAST PVT LTD - BETHAMCHERLA, KURNOOL (dt) 518599 | [7 empty] | Rev.Dt | REV DATE:
[8 empty] | DATE: | ISSUE DATE
s.no | Part no | Part Name | Grade | Customer | Mat. Grade / SIZE | MACHINE | Quantity | Weight | status/priority | Remarks
| V114035204 | M14X1.5X35 HHB | PPL-10.9 22A/F | INTERNAL | 10B35/13.65 | 164S | 18000 |  | 1164.6 | URGENT
| L114055204 | M14X1.5X55 HHB | PPL-10.9 22A/F | INTERNAL | 10B35/13.65 | 164S | 2000 |  | 171.6
| L114060204 | M14X1.5X60 HHB | PPL-10.9 22A/F | INTERNAL | 10B35/13.65 | 164S | 3000 |  | 273.6
| L114065204 | M14X1.5X65 HHB | PPL-10.9 22A/F | INTERNAL | 10B35/13.65 | 164S | 1200 |  | 117.24
| L114075204 | M14X1.5X75 HHB | PPL-10.9 22A/F | INTERNAL | 10B35/13.65 | 164S | 1200 |  | 131.04
| L114100204 | M14X1.5X100 HHB | PPL-10.9 22A/F | INTERNAL | 10B35/13.65 | 164S | 1200 |  | 168
| L014055204 | M14X2X55 HHB | PPL-10.9 22A/F | INTERNAL | 10B35/13.65 | 164S | 1000 |  | 200
| L014075204 | M14X2X75 HHB | PPL-10.9 22A/F | INTERNAL | 10B35/13.65 | 164S | 1000 |  | 200
| L014100204 | M14X2X100 HHB | PPL-10.9 22A/F | INTERNAL | 10B35/13.65 | 164S | 1000 |  | 200
| L016040201 | M16X2X40 HHS | PPL-10.9 24A/F | INTERNAL | 10B35/15.65 | 164S | 3000
| L016090402 | M16X2X90 HHB | PPL-8.8 24A/F | INTERNAL | 10B35/15.65 | 164S | 150 |  |  | CUSTOMER. SAMPLE
| L116055202 | M16X1.5X55 HHB | PPL-10.9 24A/F | INTERNAL | 10B35/15.65 | 164S | 2000
| L016055202 | M16X2X55 HHB | PPL-10.9 24A/F | INTERNAL | 10B35/15.65 | 164S | 600
| L016080202 | M16X2X80 HHB | PPL-10.9 24A/F | INTERNAL | 10B35/15.65 | 164S | 600
| L016085202 | M16X2X85 HHB | PPL-10.9 24A/F | INTERNAL | 10B35/15.65 | 164S | 600
| L016130202 | M16X2X130 HHB | PPL-10.9 24A/F | INTERNAL | 10B35/15.65 | 164S | 600
| L016150202 | M16X2X150 HHB | PPL-10.9 24A/F | INTERNAL | 10B35/15.65 | 164S | 600
[6 empty] | SUB TOTAL | 37750
[6 empty] | TOTAL | 83030
| M/C SPEED | OUTPUT/DAY IN 75% | AVAILABLE TIME OF THIS MONTH PRODUCTION {75%) | PLAN OF PRODUCTION/THIS MONTH | NO.DAYS REQUIRED BASED ON 75% OUTPUT
24 | 65PIECE/MINS | 26325 | 263250 | 83030 | 3.154
25
26
27
SIGN | PRODUCTION (C.F,ROLLING) HOD/INCHARGE |  | TOOL ROOM HOD/INCHARGE |  | QUALITY HOD/INCHARGE |  | PPC HOD/ INCHARGE
NOTE: | PRIORITY OF ITEMS BASED ON THE CUSTOMER URGENCY
PREPARED BY: | [6 empty] | APPROVED BY:

## holiday plan (hidden)
FORGING DAILY OR WEEKLY PRIORITY | [8 empty] | Format No | DOC NO:
[9 empty] | Rev no | REV NO:
PERCI FAST PVT LTD - BETHAMCHERLA, KURNOOL (dt) 518599 | [5 empty] | DATE: | FROM : | 2022-10-22 | Rev.Dt | REV DATE:
[7 empty] | TO : | 2022-10-25 | DATE: | ISSUE DATE
PRODUCTION PLANNING
s.no | Date | Part no | Part Name | Grade | Customer | Mat. Grade / SIZE | MACHINE | Quantity | Weight | status/priority | Remarks
1 | 22-10-2022 TO 25/10/2022 | G006030401 | M6X1X30 FL | 8.8 | PIC.KN | 15B25/5.75 | 64s | 10000 |  | URGENT
2 |  | A006030101 | M6X1X30 SHCS | 12.9 | KN | 4140/6.38 | 64s | 10000 |  | URGENT
3 |  | S008025581 | M8X1.2X25 HHS | GTI A270 | GUHA | 304/7.03 | 84S | 39000 |  | URGENT | PLAN DISPATCH
4 |  | W008020582 | M8X1.25X20 SHCS | PPL-A270 | GLOBAL | 304/7.03 | 84S | 100000 |  | URGENT
5 |  | W008020581 | M8X1.25X25 SHCS | PPL-A270 | GLOBAL | 304/7.03 | 84S | 100000 |  | URGENT
6 |  | CFB2711035 | M10X1.5X35 | PPL-10.9 | BEML | 15B25/9.70 | 6L4 | 14700 |  | NPD
7 |  | L016090202 | M16X2X90 HHB | PPL-10.9 | OMKAR | 15B25/15.65 | 164S | 1500 |  | URGENT
8 |  | L016090402 | M16X2X90 HHB | PPL-8.8 | AKAY | 15B25/15.65 | 164S | 2200 |  | URGENT
9 |  | L016050201 | M16X2X50 HHS | PPL-10.9 | OMKAR | 15B25/15.65 | 164S | 5000 |  | URGENT
10 |  | L012100202 | M12X1.75X100 | PPL-10.9 | OMKAR | 15B25/11.60 | 164S | 1000 |  | URGENT
11 |  | L010100202 | M10X1.5X80 HHB | PPL-8.8 | AKAY | 15B25/9.70 | 164S | 2500 |  | URGENT
12 |  | L010100202 | M10X1.5X100 HHB | PPL-8.8 | AKAY | 15B25/9.70 | 164S | 2500 |  | URGENT
13 |  | L010100202 | M10X1.5X100 HHB | PPL-10.9 | OMKAR | 15B25/9.70 | 164S | 5000 |  | URGENT
14 |  | A016095102 | M16X2X95 SHCB | PPL-12.9 | BEML | 4140/16.40 | 164S | 2500 |  | URGENT | 3RD SAMPLES
15 |  | A016070102 | M16X2X70 SHCB | PPL-12.9 | BEML | 4140/16.40 | 164S | 3000 |  | URGENT
|  | L024070204 | M24X3X70 HHB | PPL-10.9 | BEML | 15B41/23.60 | 25B4LL | 2500 |  | URGENT
SIGN |  | PRODUCTION (C.F,ROLLING) HOD/INCHARGE |  | TOOL ROOM HOD/INCHARGE |  | QUALITY HOD/INCHARGE |  | PPC HOD/ INCHARGE
NOTE: |  | PRIORITY OF ITEMS BASED ON THE CUSTOMER URGENCY

## Daily forging priority (hidden)
FORGING DAILY PRIORITY | [6 empty] | Format No | F/8.5/PP/05
[7 empty] | Rev no | 0
PUNCH RATNA FASTENERS PVT LTD - PLANT II | [6 empty] | Rev.Dt | 2018-06-02
DATE:
# | Part no | Part Name | Customer | Mat. Grade / SIZE | MACHINE | Quantity
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
22
23

## FORGING PRIORITY - (2) (hidden)
FORGING DAILY PRIORITY | [6 empty] | Format No | F/8.5/PP/05
[7 empty] | Rev no | 0
PUNCH RATNA FASTENERS PVT LTD - PLANT II | [6 empty] | Rev.Dt | 2018-06-11
[7 empty] | DATE: | 2021-08-09
# | Part no | Part Name | Customer | Mat. Grade / SIZE | MACHINE | Quantity | Weight | Remarks
1 | 311035110 | BALL PIN | RML | EN18D/26.7 | BM01 | 25000 |  | RUNNING
2 | 311035910 | BALL PIN | RML | EN18D/26.7 | BM01 | 15000
3 | 311036010 | BALL PIN | RML | EN18D/26.7 | BM01 | 10000
4 | CPGK2T11355CA | 421 PANTHER | COMSTAR | 1045H/20.35 | BM01 | 40000
5 | 321060410 | BALL PIN | RML | EN-18D/15.7 | BM02 | 20000 |  | RUNNING
6 | 321060010 | BALL PIN | RML | EN-18D/16.7 | BM02 | 10000
7 | CP0630602F00 | BALL PIN | SOMIC ZF | SCM440/17.95 | BM02 | 12000
8 | 3210215510 | BALL PIN | RML | EN-18D/17.8 | BM03 | 10000 |  | RUNNING
9 | 1441804x0101 | M16X2.0X200 | TAFE | 10B35/15.7 | BM03 | 20000
10 | 1334C01201 | M16X2.0X220 | TAFE | 10B35/15.7 | BM03 | 20000
11 | 3019903X01 | M16X2.0X260 | TAFE | 10B35/15.7 | BM03 | 6000
12 | 1090980-AA | 7/16UNFX40L | TAKATA | 15B25/11.68 | BM04 | 30000 |  | RUNNING
13 | 1106137-AA | 7/16UNFX28L | TAKATA | 15B25/11.68 | BM04 | 30000
14 | L01718687NCP | DIA10X22 PIN | KM SEAT | 10B21/13.2 | BM04 | 30000
15 | 801017000 | 7/1620UNFX40L | RANE TRW | 15B25/13.2 | BM04 | 20000
16 | CP0420002F00 | BALL ROD | SOMIC ZF | 41CR4/15.25 | BM06 | 60000 |  | RUNNING
17 | 95022-08045 | M8X1.25X45 | YAMAHA | 15B25/7.75 | BM09 | 10000 |  | NPD SETTING
18 | GT9000110C4 | M8X1.25X14.5 | MANDO | 1045H/7.75 | BM09 | 200000
19 | GJ90104400 | M6X1.0X16.6 | MANDO | 1045H/7.75 | BM09 | 200000
20 | 95022-06010 | M6X1.0X10 | YAMAHA | 10B21/5.75 | BM08 | 400000 |  | RUNNING
21 | 95022-06012 | M6X1.0X12 | YAMAHA | 10B21/5.75 | BM08 | 400000
22 | 95822-06016 | M6X1.0X16 | YAMAHA | 10B21/5.75 | BM10 | 200000 |  | RUNNING

## 120821 (hidden)
FORGING DAILY PRIORITY | [6 empty] | Format No | F/8.5/PP/05
[7 empty] | Rev no | 0
PUNCH RATNA FASTENERS PVT LTD - PLANT II | [6 empty] | Rev.Dt | 2018-06-11
[7 empty] | DATE: | 2021-08-12
# | Part no | Part Name | Customer | Mat. Grade / SIZE | MACHINE | Quantity | Weight | Remarks
1 | 311036010 | BALL PIN | RML | EN18D/26.7 | BM01 | 20000 |  | RUNNING
2 | CPGK2T11355CA | 421 PANTHER | COMSTAR | 1045H/20.35 | BM01 | 60000
3 | CPFV3S11355BA | SHAFT | COMSTAR | 1045H/20.35 | BM01 | 40000
4 | 26-300-02-F00 | BALL PIN | SOMIC ZF | 4140/18.7 | BM02 | 100000 |  | RUNNING
5 | CP0630602F00 | BALL PIN | SOMIC ZF | SCM440/17.95 | BM02 | 12000
6 | 1334C01201 | M16X2.0X220 | TAFE | 10B35/15.7 | BM03 | 20000 |  | RUNNING
7 | 3019903X01 | M16X2.0X260 | TAFE | 10B35/15.7 | BM03 | 6000
8 | 3210203213S | BALL ROD | RML | 4140/17.7 | BM03 | 13000
9 | 801017000 | 7/1620UNFX40L | RANE TRW | 15B25/13.2 | BM04 | 10000 |  | NEXT
10 | FYL07311 | M10x1.5x30 FLANGE SCREW | AL | 15B25/10.3 | BM04 | 30000
11 | 1090980-AA | 7/16UNFX40L | TAKATA | 15B25/11.68 | BM04 | 30000
12 | 1106137-AA | 7/16UNFX28L | TAKATA | 15B25/11.68 | BM04 | 30000
13 | CP0420002F00 | BALL ROD | SOMIC ZF | 41CR4/15.25 | BM06 | 60000 |  | RUNNING
14 | GT9000110C4 | M8X1.25X14.5 | MANDO | 1045H/7.75 | BM09 | 200000
15 | FYL07211 | M8x1.25x25 FLANGE SCREW | AL | 152B5/7.7 | BM09 | 100000
16 | GJ90104400 | M6X1.0X16.6 | MANDO | 1045H/7.75 | BM09 | 200000
17 | 95022-06010 | M6X1.0X10 | YAMAHA | 10B21/5.75 | BM08 | 400000 |  | RUNNING
18 | 95022-06012 | M6X1.0X12 | YAMAHA | 10B21/5.75 | BM08 | 400000
19 | 90101-06814-00-80 | M6X1.0X30 | YAMAHA | 10B21/5.75 | BM10 | 150000 |  | NEXT

## 160821 (hidden)
FORGING DAILY PRIORITY | [6 empty] | Format No | F/8.5/PP/05
[7 empty] | Rev no | 0
PUNCH RATNA FASTENERS PVT LTD - PLANT II | [6 empty] | Rev.Dt | 2018-06-11
[7 empty] | DATE: | 2021-08-16
# | Part no | Part Name | Customer | Mat. Grade / SIZE | MACHINE | Quantity | Weight | Remarks
1 | CPGK2T11355CA | 421 PANTHER | COMSTAR | 1045H/20.35 | BM01 | 60000 |  | RUNNING
2 | CPFV3S11355BA | SHAFT | COMSTAR | 1045H/20.35 | BM01 | 40000
3 | CP0630602F00 | BALL PIN | SOMIC ZF | SCM440/17.95 | BM02 | 12000 |  | RUNNING
4 | 321011110 | BALL PIN | RML | EN-18D/17.4 | BM02 | 12000
5 | 321011210WOP | BALL PIN | RML | EN-18D/17.4 | BM02 | 10000
6 | 321059310 | BALL PIN | RML | EN-18D/14.8 | BM03 | 35000 |  | SETTING
7 | 3210215110 | BALL PIN | RML | EN-18D/17.8 | BM03 | 20000 |  | NPD
8 | B44F214110 | M12X1.5X247 | YAMAHA | 15B25/11.68 | BM03 | 10000
9 | 1090980-AA | 7/16UNFX40L | TAKATA | 15B25/11.68 | BM04 | 30000 |  | RUNNING
10 | 1106137-AA | 7/16UNFX28L | TAKATA | 15B25/11.68 | BM04 | 30000
11 | CP0420002F00 | BALL ROD | SOMIC ZF | 41CR4/15.25 | BM06 | 60000 |  | RUNNING
12 | GT9000110C4 | M8X1.25X14.5 | MANDO | 1045H/7.75 | BM09 | 200000 |  | RUNNING
13 | FYL07211 | M8x1.25x25 FLANGE SCREW | AL | 152B5/7.7 | BM09 | 100000
14 | GJ90104400 | M6X1.0X16.6 | MANDO | 1045H/7.75 | BM09 | 200000
15 | 95022-06010 | M6X1.0X10 | YAMAHA | 10B21/5.75 | BM08 | 400000 |  | RUNNING
16 | 95022-06012 | M6X1.0X12 | YAMAHA | 10B21/5.75 | BM08 | 400000
17 | 90101-06814-00-80 | M6X1.0X30 | YAMAHA | 10B21/5.75 | BM10 | 150000 |  | RUNNING
18 | 9751206525 | M6X1.0X25 | YAMAHA | 10B21/5.75 | BM10 | 300000

## closed (hidden)
S.NO | PRIORITY | DEPT | DATE | (MOM) PROBLEM DESCRIPTION | ACTION | RESP | TARGET | STATUS
1 | MEDIUM | HR |  | OPERATOER LEAVE POLICY |  | HR |  | COMPLETED
2 | MEDIUM | PROD |  | PRODUCTION CONSUMABLES SPARES INDENT TO BE HAND OVER TO CONCERN DEPARTMENT |  | DILLI |  | COMPLETED
3 |  | PROD |  | PRODUCTION MACHINE WISE PLAN TO BE CIRCULATE FOR CONCERN DEPARTMENT |  | DILLI |  | COMPLETED
4 |  | PROD |  | MACHINE HANDOVER TO MNT BASED ON PRODUCTION PLAN & TIMING PLAN 164S |  | UMA MAHESH |  | COMPLETED
5 |  | PROD |  | TK250 CUTTER BROKEN | WELDING WORK DONE | DILLI |  | COMPLETED
6 |  | MNT |  | HEAT EXCHANGER PROBLEM-HT | HEAT EXCHANGER CLEANING & RE ASSEMBLY | UMA MAHESH | 2024-03-28 | COMPLETED
7 |  | MNT |  | DPR 8S1 MOTOR RE ASSEMBLY WORK | FITTED IN MACHINE | UMA MAHESH | 2024-03-28 | COMPLETED
8 |  | TOOL |  | 64S MACHINE NPD PLAN | MAKE A DETAILED TIME PLAN AND RELEASE | PARAMA | 2024-03-29 | CLOSE
9 |  | NPD |  | TK250 SLIDING PUNCH DRAWING APPROVAL PENDING | PUNCH & PIN DRAWING RELEASE | GRUINDER | 2024-03-28 | CLOSE
10 |  | PUR |  | RM ARRIVAL SCHEDULE | RECEIPT TIMING & QTY TO BE CONFIRMED | RAJESH | 2024-03-28 | COMPLETED | REGULAR INFORMATION TO BE DONE
11 |  | STR |  | OUTSOURCES MATERIAL SHOTAGE PROBLEM | MENTION THE WEIGHT IN THE TAG WHILE DISPATCHING TO SECONDARY OPERATIONS | NAGARAJ | NEXT LOT | COMPLETED
12 |  | PROD |  | M6 X1X12 PHS DIE CHIPOFF 1ST STATION (LIFE ACHIVED 20000 NOS) | CHIFOFF ROOT CAUSE ANALIYSIS TO BE DONE | DILLI | 29.03.2024 | COMPLETED
13 |  | PROD |  | TRUB MACHINE OUTPUT GAP | NEED TO VERFIY THE LOG BOOK | DILLI | 2024-03-29 | COMPLETED
14 |  | TOOL |  | TK250 DIES & TOOLS DIE BROKEN NO SPARE STOCKS | NEED TO ORDERED FOR M6 3 NOS | PARAMA/RAJESH | 30.03.2024 | COMPLETED | TOOLS ORDERED
15 |  | TOOL |  | M6X1X12 PHS ORDER CANCEL FORM CUSTOMER DUE SUPPLY FAILUARE | TOOL INDENT NEED TO RASIE TODAY & PURCHASE ON URGENT BASIS | PARAMA/RAJESH | 30.03.2024 | COMPLETED | PENDING
16 |  | TOOL |  |  | EXISTING TOOL COUNTER MEASURE DESIGN CHANGE 8 NOS NEED TO ORDER | PARAMA | 30.03.2024 | COMPLETED
17 |  | NPD |  | 64S M5X0.8X13 FL SHORT CLOSE DUE TO SLIDING PUNCH BROKEN | PROCUREMENT OF NEW PUNCH & NEW NPD PLAN TAKEN(SPHERICAL FL) | PARAMA | 30.03.2024 | COMPLETED
18 |  | TOOL |  | HEADING PUNCH NOT ISSUEN DUE TO IMPROPER ASSEMBLY | ASSEMBLY METHODLOGY TO BE STANDARDISED AND TRAINED | PARAMA | 2024-04-01 | COMPLETED
19 |  | PROD |  | M24 MTE HHB PLAN FOR SINGLE ROLLING DUE TO QA ISSUE WE ARE PLANNING DOUBLE ROLLING | FOLLOWUP FOR M/C RECEIT & TRAILS | DILLI/NARASIMHA | 2 MONTH | COMPLETED
20 |  | TOOL |  | TOOL & CUTTER SPLINDLE BEARING NOISE | NEED TO REPLACE WITH NEW BEARINGS | UMA MAHESH | 30.03.2024 | COMPLETED
21 |  | PUR |  | NOTICE BOARD ORDERING | PO NEED TO CONFIRM TODAY | RAJESH | 2024-04-06 | COMPLETED | AWAITIG FOR APPROVAL
22 |  | ST |  | METALMAN AUDIT POINT CLOSER INTERNALLY | SUMBIT ACTION PLAN TO QA | NAGARAJ | 2024-04-04 | COMPLETED
23 |  | PUR |  | M10X1.5 SS SERIES PRODUCT SHORT CLOSE DUE TO RM SHORTAGE | MATERIAL INTRANSIT | RAJESH |  | COMPLETED | PENDING
24 |  | PROD |  | M10X1.5 SS SERIES PRODUCT A/C DAMEGE | ROOTCAUSE TO BE REVIWED FOR ACTION | DILLI | 2024-04-04 | COMPLETED
25 |  | PUR |  | RING GAUGES PURCHASE | RING GAUGES TO BE ARRANGED | RAJESH |  | COMPLETED | BY DISCUSSING WITH SUPPLIER TARGET DATE TO BE REPORTED
26 |  | QA |  | LACTOTITE OPERATORS TRAINING | FOR QULAITY CONFIRMATION WITH OK-NG MASTER SAMPLES TO BE MADE | SAMI | 2024-04-04 | COMPLETED
27 |  | PROD |  | DD BOLT CUSTOMER COMPLIANT | DESIGN REVIEW REQUIRED & CFT | PROD | 2024-04-17 | COMPLETED
28 |  | PROD |  | TURNING BITS REQUIRED( TRUB) | TOOL INDENT NEED TO RASIE TODAY & PURCHASE ON URGENT BASIS | RAJESH | 2024-04-18 | COMPLETED
29 |  | NPD |  | 64S MACHINE NPD LAC00010-SLHCS-M6 X 15, 2ND AND 3RD STATION DIE TRD NOT MATCHING | DESIGN REVIEW AND NEW DIE PROCUREMENT AS PER NEW DESIGN | GURINDER/PARANDAM | 2024-05-09 | COMPLETED
30 |  | TOOL |  | M16X1.5 NUT,TAP BITS REQUIRED | TAP BITS TO ORDERED | PARANDAMA/RAJESH | 2024-05-01 | COMPLETED
31 |  | PROD |  | HAND GLOVES SHORTAGE | NORMS TO BE DIFINED FOR MINIMUM QTY'S TO BE AVILABLE | RAJESH/DILLI | 2024-04-22 | COMPLETED
32 |  | TOOL |  | JY BOLT 4TH STATION DIE AND CASE STOCK ISSUE | TO BE PROCURED | RAJESH/PRANDAMA |  | COMPLETED | WILL BE REVERTED BY 23-APRIL.PI RECEIVED WILL COME
33 |  | MKTG |  | 8D SUBMISSION FOR CFB2510816 HEX BOLT | 8D REPORT TO BE PROVIDED BY MARKETING | BALAKRISHNA | 2024-04-23 | COMPLETED
34 |  | QA |  | M10X1.25X22.8 SNAP GAUGE USE IN LINE | GAUGE STOCK (ROR) INCREASED | SAMI | 2024-04-26 | COMPLETED
35 |  | TOOL |  | M10X1.25X27 TRIMMING HEAD BEND DUE TO MORE LOAD ON CUTTING | CUTTING FORCE REDUCE BY ADDING WASHER AT 3RD STN | PARANDAAMA | 2024-04-25 | COMPLETED
36 |  | TOOL |  | DH--TRIM DIE -KAIZEN TRAIL | SUMMARY TO BE CONSALIDATED AND SUBMITTED TO THE TEAM | PARANDAAMA | 2024-04-29 | COMPLETED
37 |  | HR |  | MEETING DETAIILS | HR TO RECORD PRESENT THE ATTENDANCE FOR TRACING | HR | 2024-04-29 | COMPLETED
38 |  | PPC |  | RM SHORTAGE ISSUE | FOR M24/M8/M14/M16 /M10 RM TO BE ORDERDED | DILLI | 2024-05-08 | COMPLETED
39 |  | PUR |  | RPO OIL/PACKING MATERIALS | APRIL -24 INDENTED MATERIAL TO BE RECEIVED | RAJESH/NAGARAJ | 2024-05-09 | COMPLETED
40 | HIGH | MNT | 2024-05-16 | POWER FAILURE ISSUE | FLASH REPORT WITH ACTION PLAN TO BE RELEASED | UMA MAHESH | 2024-05-17 | COMPLETED
41 | HIGH | PROD | 2024-05-16 | M10-DIA 36 COLLAR | DEVIATION NOTE BE RAISED | DILLI | 2024-05-17 | COMPLETED
42 | HIGH | PROD | 2024-05-18 | FIRST STN PLAIN BORE DIE NOT AVILABLE | FIRST STN PLAIN BORE DIE TO BE PROCURED, M14 PLAIN BORE DIE COVERTING INTO M10 FLANGES, | PARAM |  | COMPLETED
43 | HIGH | TOOL | 2024-05-20 | DH-PREPOINTING DIE REQUIRED | PREPOINTING DIE TO BE OREDERED | PARAM | 2024-05-21 | COMPLETED
44 | HIGH | TOOL | 2024-05-20 | DH-2ND & 3RD STATION DIES REQUIRED | 2ND & 3RD STATION DIES REQUIRED | PARAM | 2024-05-21 | COMPLETED
45 | HIGH | TOOL | 2024-05-21 | JUNE MONTH SCHUDELES TOOL ORDERING | ORDERING TO BE REVIEWED AND PROCURED | PARAM | 2024-05-21 | COMPLETED
46 | HIGH | MNT | 2024-05-22 | USED OIL REUSE | USED COLD FORGING OIL FOR REFILLING PURPOSE CAN BE USED OR NOT TO BE TAKEN CONSULATION | UMA MAHESH | 2024-05-25 | COMPLETED | CANNOT BE USED FOR COLD FORGING
47 | HIGH | TOOL | 2024-05-25 | M8X16 & 30 BUTTON HEAD FORGING PENDING | 3rd PUNCH INSERT REQUIRED | RAJESH | 2024-05-27 | COMPLETED
48 | HIGH | PUR | 2024-05-27 | FLANGE BOLT M16X1.5X100 & 80 FORGING PENDING | TOOLS TO BE PURCHASED-(REWORK WILL BE DONE) | PARAM |  | COMPLETED | TARGET DATE TO BE DECIDED BY 27-05-2024.
49 | HIGH | QA | 2024-05-30 | QUALITY SLOGANS | TO BE DISPLAYED ACROSS QULAITY AREA | BRIJESH | AS PER DATE | COMPLETED
50 | HIGH | PPC | 2024-05-30 | 64S-HEX PINS REQUIRED | TO BE PROCURED ASAP | RAJESH | 2024-06-07 | COMPLETED
51 | HIGH | PPC | 2024-05-30 | 84S-HEX PINS/BHS PINS REQUIRED | TO BE PROCURED ASAP | RAJESH | 2024-06-07 | COMPLETED
52 | HIGH | PPC | 2024-05-30 | 6L4-17A/F TRIM DIE/KNURLING DIE REQUIRED | TO BE PROCURED ASAP | RAJESH | 2024-06-07 | COMPLETED
53 | HIGH | PPC | 2024-05-30 | 164S-M10/16 FL TOOLS REQUIRED | TO BE PROCURED ASAP | RAJESH | 2024-06-07 | COMPLETED
54 | HIGH | PROD | 2024-06-04 | 164S-2ND STATION TOOL ASSEMBLY STUCK UP | CORRECTIVE ACTIONS FOR TOOL ASSEMBLY TIGHTENING AND BORE SIZES MISMATCH | DILLI/PARANDAMA | 2024-06-04 | COMPLETED
55 | HIGH | TOOL | 2024-06-04 | M22 TOOL CONVERSATIONS | M20 TO M22 TOOL CONVERSATIONS TO BE DONE | DILLI/PARANDAMA | 2024-06-06 | COMPLETED
56 | HIGH | PUR | 2024-06-05 | THREAD PROTECTORS STOCKS | PAYMENTS TO BE PAID ON URGENT BASIS TO PROCURE | RAJESH | 2024-06-05 | COMPLETED
57 | HIGH | TOOL | 2024-06-05 | TK-250 FIRST SLIDING PUNCH DAMAGE | SOLID CARBIDE TOOLS NEED TO BE CONVERTED | PARANDAMA | 2024-06-05 | COMPLETED
58 | HIGH | PROD | 2024-06-07 | TK-250 PUNCH PIN DAMAGE | PUNCH PIN MODIFICATION TO BE MADE | DILLI | 2024-06-07 | COMPLETED
59 | HIGH | TOOL | 2024-06-12 | JY 2ND AND 3RD STAGE DIE ORDER STATUS | EXPECTED ON AND ORE BEFORE 15-JUNE-20224 | RAJESH | 2024-06-15 | COMPLETED
60 | HIGH | PROD | 2024-06-15 | FORGING OPERATOR-ONE TO ONE REVIEW | PRODUCTION PERFORMANCE TO BE REVIEWD ON DAILY BASIS | DILLI | 2024-06-15 | COMPLETED
61 | HIGH | TOOL | 2024-06-15 | PRODUCTION/TOOL/PURCHASE WEEKLY MEETING | SUCCESSFULLY COMPLETED ON 14-JUNE-2024 | RAJESH/DILLI/PARANDAMA | 2024-06-15 | COMPLETED
62 | HIGH | PPC | 2024-06-17 | SUNDAY AND WEEKLY PLANNING IMPROVEMENTS | EVERY WEEK FRIDAY SUNDAY AND NEXT WEK PLAN TO BE FREEZED | DILLI/BALA | 2024-06-21 | COMPLETED
63 | HIGH | TOOL | 2024-06-19 | M25LL-M22 TRIM DIE PREPARENESS | IN TOOL ROOM DIE REWORK AND TO BE ISSUED | NAGARAJUNA | 2024-06-19 | COMPLETED
64 | HIGH | PROD | 2024-06-20 | MTE HOURLY PLAN | HOURLY PLAN TO CHECKED AND CONSOLIDATED | NANDINI | 2024-06-21 | COMPLETED
65 | HIGH | PPC | 2024-06-20 | JY/DH WIP STATUS | TRAINING FOR GET FOR WIP OF DH/JY | NAGARAJ | 2024-06-21 | COMPLETED
66 | HIGH | PPC | 2024-06-24 | JUNE-WEEK 5 PLAN RELEASE | BY 1:00PM THE PLAN TO BE RELEASED | DILLI | 2024-06-24 | COMPLETED
67 | HIGH | TOOL | 2024-06-24 | 254L-3RD STATION HEADING INSERT STUCK UP | TO BE REMOVED WITH HELP OF TURNING | PARANDAMA | 2024-06-24 | COMPLETED
68 | HIGH | TOOL | 2024-06-26 | BORE/HOLE GAUAGE NOT AVAILBLE | INDENT AND TO BE PROCURED | PARANDAMA | 2024-06-26 | COMPLETED
69 | HIGH | QA | 2024-06-27 | DD BOLT BOLTON DIE-TRIMING DIE ACROSS CORNER ISSUE TO SUIT TO GUAGE | SPECIFICATIONS RELATED CONCLUSIONS AND DRAWING TO BE FREEZED | PARANDAMA/BALA | 2024-06-27 | COMPLETED
70 | HIGH | TR/PROD | 2024-06-27 | TK250-SLIDING CONE PUNCH ANGLE NEED TO REVISE-M6 X 10-PHS | TOOL REWORK AND ECR NEED TO RAISE | PARANDAMA/DILLI | 2024-06-27 | COMPLETED
71 | HIGH | PUR |  | 1ST TROP DIE NOT AVAILABLE | NEW TROP DIES ORDERED (5 NOS) | RAJESH | 2024-04-14 | COMPLETED | NEGOCIATE DATE WITH SUPPLIER FOR EARLIY RECEIPT. EXCEPT MATERIAL 07/05/2024
72 | HIGH | TOOL |  | TK250-M5 2ND PUNCH INSERT | ORDERED FOR 70 NOS | RAJESH | 2024-06-13 | COMPLETED | TARGET DATE TO BE CONFIRMED
73 | HIGH | PROD |  | COTTON WASTER-SHORTAGE | PROCUREMENT TEAM TO ORDER | RAJESH |  | COMPLETED
74 | HIGH | PPC | 2024-05-30 | 84S-HEADING INSERTS(A800) REQUIRED | TO BE PROCURED ASAP | RAJESH | 2024-06-10 | COMPLETED
75 | HIGH | PUR | 2024-06-05 | M12 X 1.75 ROLLING DIE NOT AVAILBALE | ROLLING DIE OREDERED(IMPORTED) | RAJESH | 2024-07-20 | COMPLETED
76 | HIGH | TR/PUR | 2024-06-14 | 17A/F TRIM DIE | BASED ON TOOL RECIPT DATES WE WILL PLAN THE DISPATCH DATE | RAJESH/PARANDAMA | 2024-06-19 | COMPLETED
77 | HIGH | PPC | 2024-06-24 | KRAFT PAPER UNAVAILBLE | ORDERED MATERIAL STATUS | RAJESH | 2024-06-24 | COMPLETED

## open TILL 30 june (hidden)
S.NO | PRIORITY | DEPT | DATE | (MOM) PROBLEM DESCRIPTION | ACTION | RESP | TARGET | STATUS
1 | HIGH | MNT |  | 164S MAINTENANCE ACTIVITY PLAN | PLAN NEED TO BE PREPARE REALSE | UMA MAHESH | 2024-04-04 | OPEN
2 | HIGH | MNT |  | 84S MAINTENANCE ACTIVITY PLAN, |  | UMA MAHESH |  | OPEN
3 | HIGH | MNT |  | 64S MAINTENANCE ACTIVITY PLAN | DETAILED ACTIVITY PLAN WILL BE MADE & GET IT REVIEW | UMA MAHESH | 2024-03-29 | OPEN
4 |  | MNT |  | 84S MAIN MOTOR BREAKDOWN DUE TO BEARING ISSUE | ARRANGE THE SLEEVE & BEARINGS AND CLEAR THE ISSUE | UMA MAHESH |  | OPEN
5 |  | MNT |  |  | STEP WISE ACTION TO BE MADE TO TAKE OUT THE SLEEVEAND DRIVE THE DRAWING (6HR) | UMA MAHESH | 2024-03-28 | OPEN
6 |  | MNT |  |  | NEAR TO CHECKNUT PUT A WELDING POT AND RUN THE LINE | UMA MAHESH | 2024-03-28 | OPEN
7 |  | MNT |  |  | ANBOND MIN STOCK TO BE UPDATE IN MNT CONSUMABLE LIST | UMA MAHESH | 2024-03-28 | OPEN
8 |  | HR |  | ITI FRESHER RECUREMENT | 10 MEMBERS PLANNING TO BE INITIATED | HR | 2024-04-05 | OPEN
9 |  | MNT |  | 3RD STN PUNCH LOCKING SCREW DEMAGED | REPAIR BY WELDEING AND RE TAPPING | UMA MAHESH | 2024-03-29 | OPEN
10 |  |  |  |  | PERMENT ACTION TO BE REPORTED | UMA MAHESH | 2024-03-30 | OPEN
11 |  |  |  |  | MANPOWER ISSUE | HR | 30.03.2024 | OPEN
12 |  | MNT |  | DPR 8S TRACK MODIFICATION REQUIRED | TRACK LEVELING REQUIRED( OUTSOURCES ACTIVITY) | UMA MAHESH | 2024-04-05 | OPEN
13 |  | MNT |  | CRANE PARTS PROCUREMENT AND ASSEMBLY | PARTS TO BE ORDERED PROJECT TO BE COMPLETED | UMA MAHESH | 2024-04-06 | OPEN
14 |  | MNT |  | 25B4LL MACHINE SPRE GOT DAMEGE | EXTERNAL SERVICES TO BE PLANNED | UMA MAHESH | 2024-04-03 | OPEN
15 |  | PUR |  | M8X1.25X20 PRODUCTS FINGER MARKS PROBLEM B DUE TO PLAY IN TRANSFER UINTS & FINGER DIEMENSION DESIGN ISSUE & SETTING ISSUE | ROOTCAUSE TO BE REVIWED FOR ACTION | DILLI | 2024-04-04 | OPEN
16 |  | HT |  | SATIN FINISHIG LINE ACTIVITY | PLAN NEED TO BE PREPARE REALSE | RAJU/SAMY | Next month | OPEN
17 |  | PUR |  | 6L4- 3RD STN EXTRUSION DIE NOT AVILABLE | NEED TO BE PURCHASE | RAJESH | 2024-04-04 | OPEN | NEED TOOL INDENT
18 |  | PROD |  | M6 KNURLING TOOLS ISSUE ON SETTING | DESIGN REVIEW REQUIRED & CFT | DILLI | 2024-04-12 | OPEN
19 |  | MNT |  | 84S PUNCH LOCKING SCREW BROKEN CONTINUE | SCREW TO BE ARRANGE | UMA MAHESH | 2024-04-12 | OPEN
20 |  | PUR |  | M14,M12 NUT TOOL STATUS | TOOL INDENT NEED TO RASIE TODAY & PURCHASE ON URGENT BASIS | RAJESH | 2024-06-30 | OPEN | SHARNYA TOOLS TAKEN BACK THE PRESENT TOOL FOR REPLACEMENT-5-JUN-2024
21 |  | PUR |  | M5 PHS PINS CONTINUE BROKEN | DESIGN ACTION COMPLETED & PIN ORDERED | PARANDAMA | 2024-04-15 | OPEN
22 |  | PROD |  | DD BOLT PLAN SUBMISSION | PLAN NEED TO SEND TO VENDOR | PPC | 2024-04-17 | OPEN
23 |  | HT |  | LOCTITE MACHINE CAPACITY SHEET | PREPARE AND RELEASE | RAJU | 2024-07-10 | OPEN
24 |  | PROD |  | M5 PHS PINS CONTINUE BROKEN | TEMPORARY M5 PINS TO BE ORDERED | PROD | 2024-04-18 | OPEN
25 |  | NPD |  | JY-KAIZEN-3RD STATION DIE REQUIRED | NEW DIE ORDERED TO BE RECEIVED(3 NO'S) | RAJESH | 2024-05-04 | OPEN
26 |  | PROD |  | 84S MACHINE-PUNCH CASE & SAFETY BOLT BROKEN | PKO TO BE CHECKED & PUNCH CASE LOCKING SLOT DEPTH TO BE CHECKED | DILLI/PARANDAMA | 2024-04-22 | OPEN | PKO IS CORRECT,SHORT FEED ISSUE
27 |  | HR |  | ACCIDENT OCCURED IN PLANT ON 20-APRIL | REPORT TO BE RELEASED | HR | 2024-04-22 | OPEN
28 |  | MNT |  | SHORT FEED SENSOR IN 84S | TO BE ACTIVATED TO AVOID THE SHORT FEED ISSUE | UMA MAHESH | 2024-04-23 | OPEN
29 |  | MNT |  | FEEDING GEAR WHEEL TEETH WEAR COMING | TO OPEN THE GEAR WHEEL AND CHECK THE CONDITION | UMA MAHESH | 2024-04-23 | OPEN
30 |  | MNT |  | HEADER NOT WORKING DUE TO ELECTRICAL ISSUE | TO BE CONSULTED WITH THE SERVICE PERSON | UMA MAHESH | 2024-04-23 | OPEN
31 |  | MNT |  | 64S PUNCH BLOCK TO BE ORDERED | PO TO BE RELASED ON PRIORITY | UMA MAHESH | 2024-04-24 | OPEN
32 |  | MNT |  | 84S TO BE RELEASED TO MAINTENCE ON 25-APRIL-2024 IN SECOND HALF | 84S MAINTENCE PLAN | UMA MAHESH | 2024-04-25 | OPEN
33 |  | TOOL |  | JY-KAIZEN-TRIM DIE LIFE | SUMMARY TO BE CONSALIDATED AND SUBMITTED TO THE TEAM | PARANDAAMA | 2024-04-26 | OPEN
34 |  | HR |  | CLOCKS AT SHOP FLOOR | NEW CLOCKS TO BE PROCURE AND DISPLAY AT OPERATION AREAS | HR |  | OPEN
35 |  | PROD |  | H.T RM ARRIVAL SCHEDULE | FOLLOWUP FOR M24 COILS | DILLI | 2024-04-29 | OPEN
36 |  | PROD |  | SECONDARY OPEARATION CONSUMABLE LIST & WEAR PARTS DETAILS | PREPARE AND RELEASE | NAGA | 2024-04-29 | OPEN
37 |  | MNT |  | COLONY - POINTING MACHINE SHIFTING | TO BE SHIFITED TO PLANT & COMMISION | UMA MAHESH | 2024-05-06 | OPEN
38 |  | QA |  | TOOLS/ SPARES/DIES ORDERING RESPONSIBILITY DEFINE | CHECK THE CURRENT PROCEDURE | BRIJESH | 2024-05-06 | OPEN | REVEISION REQUIRED
39 |  | PPC |  | LAC-59 DETAILS DISPATCH PLAN | FROM INPUT TO DISPATCH | DILLI | 2024-05-07 | OPEN
40 |  | MNT |  | M16- ROLLING MACHINE MNT ( THREAD DAMAGE) | THREADED BUSH ORDER AND REPLACE | UMA MAHESH |  | OPEN | TARGET DATE TO BE CONFIRMED
41 |  | TK250 |  | RAMPLAY PROBLEM |  | UMA MAHESH |  | OPEN
42 |  | MNT |  | M16-ROLLER STUCK UP AND WEAR OUT | PB MATERIAL ROLLERS TO BE DEVELOPED | UMA MAHESH | 2024-05-18 | OPEN
43 |  | MNT |  | DPR8 ROLLING MACHINE SERVICE | PLAN TO BE MADE AND PROBLEM POINTS TO BE RECTIFIED | UMA MAHESH |  | OPEN | DERIVE THE PLAN AND DECIDE THE TARGET DATE
44 | MEDIUM | QA | 2024-05-16 | BAJAJ AUDIT-FEEDBACK | MEETING TO BE CALLED | BRIJESH | 2024-05-17 | OPEN | MEETING WILL BE CALLED BY 21-MAY
45 | HIGH | PROD | 2024-05-16 | OPERATOR TRAINING | PLAN TO MAKE SUBMIT | DILLI | 2024-05-17 | OPEN | DATE REVISED TO 22-MAY
46 | HIGH | PPC | 2024-05-16 | HT PLAN TO BE RELEASED | REVIEW AND SUBMIT BY 16-MAY-24 | DILLI | 2024-05-17 | OPEN
47 | HIGH | MNT | 2024-05-16 | 6L4/164S-ARM SPARES REQUIRED | ORDER AND RECIPT STATUS TO BE CONFIRMED | UMA MAHESH | 2024-05-17 | OPEN | TENTATIVELY EXPECTED BY 22-JUNE-2024
48 | HIGH | PROD | 2024-05-17 | OPERATOR TRAINING TO MODIFY | REVIEW AND SUBMIT BY 18-MAY-24 | DILLI | 2024-05-18 | OPEN | DATE REVISED TO 22-MAY
49 | HIGH | HR | 2024-05-17 | OPERATOR SKILL MATRIX | CURRENT PRACTICE DOCUMENTS TO BE SHOWN | HARI | 2024-05-18 | OPEN
50 | HIGH | PPC | 2024-05-17 | JY CRITICAL DISPATCH | 15K TO BE SENT 20-MAY | DILLI | 2024-05-20 | UNDER PROGRESS
51 | HIGH | PPC | 2024-05-17 | PENDING ORDER TO BE MADE | PLAN AND REVIEW | DILLI | 2024-05-17 | UNDER PROGRESS | DATE REVISED TO 22-MAY
52 | HIGH | NPD | 2024-05-17 | NPD PLAN V/S ACTUAL | PLAN AND REVIEW WITH VP | PARAM | 2024-05-17 | OPEN
53 | HIGH | PPC | 2024-05-17 | M20 PARTS ROLLING | PLAN AT HYDERABAD ON URGENT BASIS | DILLI | 2024-05-17 | DILLI:AS DISCUSSED WITH MD TO BE TAKEN UP AT INHOUSE
54 |  |  |  |  | M14 PLAIN BORE DIE TO BE ORDFERED(5 NO'S) | PARAM |  | OPEN
55 | HIGH | MNT | 2024-05-20 | 84S-FEEDING AND STRAIGHTNER | BRASS ROLLER ORDERED WILL UPDATE THE STAUS | UMA MAHESH | 2024-05-20 | OPEN | UPDATE BY 21-MAY
56 | HIGH | MNT | 2024-05-20 | 164S-FEEDING AND STRAIGHTNER | BRASS ROLLER ORDERED WILL UPDATE THE STAUS | UMA MAHESH | 2024-05-20 | OPEN | UPDATE BY 21-MAY
57 | HIGH | TOOL | 2024-05-20 | DH-PREPOINTING DIE REQUIRED | PREPOINTING DIE TO BE OREDERED | RAJESH |  | OPEN
58 | HIGH | TOOL | 2024-05-20 | DH-2ND & 3RD STATION DIES REQUIRED | 2ND & 3RD STATION DIES REQUIRED | RAJESH | 2024-06-27 | OPEN
59 | HIGH | MNT | 2024-05-21 | TK250 MACHINE RAM PLAY(WORN OUT) | PERMENT ACTION TO BE REPORTED | UMA MAHESH | 2024-05-22 | OPEN
60 | HIGH | MNT | 2024-05-21 | 64S TRANSFER CASE PLAY | CIRCULAR SIM ADJUSTMENTS TEMPORARLY | UMA MAHESH | 2024-05-21 | OPEN
61 | HIGH | PROD | 2024-05-21 | 164S/84S/6L4 ROLLER REQUIRED | 164S/84S/6L4 ROLLER ORDERED-STATUS UPDATE REQUIRED | RAJESH | 2024-05-21 | OPEN | EACH SIZE WISE ARRIVAL SCHUDELE WILL UPDATE ON 21-MAY
62 | HIGH | MNT | 2024-05-21 | DPR SEPARATERS SPRING REQUIRED | SPRINGS TO BE PROCURED AND UPDATE THE STATUS | UMA MAHESH | 2024-05-21 | OPEN
63 | HIGH | PPC | 2024-05-21 | JUNE MONTH SCHUDELES RM ORDERING | ORDERING TO BE REVIEWED AND PROCURED | DILLI | 2024-05-21 | OPEN
64 | HIGH | HR | 2024-05-21 | EMPLOYEES ID CARD PLAN | ID CARDS WILL BE ARRANGED | HARI | 2024-06-01 | OPEN
65 | HIGH | MNT | 2024-05-21 | NIGHT SHIFT POWER OFF | UTILITY TEAM HAS TO REVIEW AND POWER OFF THE LIGHTS WHICH IS UNSED | UMA MAHESH | 2024-05-22 | OPEN
66 | HIGH | PRD | 2024-05-21 | 164S - OEE LOSSES | NEED TO PREPARE AND SUBMITE THE MANAGEMENT | DILLI | 2024-05-27 | OPEN
67 | HIGH | PPC | 2024-05-21 | COIL WEIGHT | EACH COIL WEIGHT NEED TO DEMAND FROM SUPPLIER | DILLI/RAJESH | 2024-05-27 | OPEN
68 | HIGH | MNT | 2024-05-21 | RM STANDS | RM STANDS REQUIRED | UMA MAHESH | 2024-06-04 | OPEN
69 | HIGH | TOOL | 2024-05-24 | 164S-DH BOLT-1ST & 2ND STATION DIE MATCHING ISSUE AND POOR LIFE | DIE KAIZEN WILL BE IMPLEMENTED FOR 2 LOTS AND FINAL REPORT | PARAM | 2024-06-24 | OPEN
70 | HIGH | HR | 2024-05-25 | BUFFING OUTPUT ISSUE | MANPOWER TO BE INCREASED | ESWAR/HARI |  | OPEN | 25-05-2024 WILL SUBMIT THE DATE
71 | HIGH | TOOL | 2024-05-25 | M8X25 (A800) SOCKET KNURLING PENDING | M8 KNURLING DIES TO BE PURCHASED | RAJESH |  | OPEN
72 | HIGH | HT | 2024-05-25 | QUENCH OIL ISSUE | PURIFICATION ACTIVITY TO BE INTEATED | RAJU | 2024-07-17 | OPEN
73 | HIGH | QA | 2024-05-29 | DD BOLT GUAGE ISSUE | GAUGE TO BE REWORKED | BRIJESH/SAMI | 2024-06-06 | OPEN
74 | HIGH | QA | 2024-05-29 | DD BOLT 16A/F & 19A/F ONE SET OF GAUAGES | DD BOLT 16A/F & 19A/F ONE SET OF GAUAGES TO BE ORDERED | BRIJESH/SAMI | 2024-06-13 | OPEN
75 | HIGH | TOOL | 2024-05-29 | M10 THREAD ROLLING DIES NOT AVILABLE | DIES ARE AT SUPPLIER END TO BE DISPATCHED | RAJESH | 2024-06-01 | OPEN
76 | HIGH | TOOL | 2024-05-29 | M16 THREAD ROLLING DIES NOT AVILABLE | DIES ARE AT SUPPLIER END TO BE DISPATCHED | RAJESH | 2024-06-01 | OPEN
77 | HIGH | QA | 2024-05-30 | QULAITY MONTH TO BE CELEBTRATED IN 2024 | IT IS SHOULD BE PLANNED AT DEPLOYED ACROSS PLANT | BRIJESH | AS PER DATE | OPEN
78 | HIGH | STORES | 2024-05-30 | EASTERN STICKERS HAS DISPATCHED TO MEGA MOTORS | CAPA TO REPORT ON THIS ISSUE | NAGARAJ | 2024-06-01 | OPEN
79 | HIGH | PROD | 2024-05-31 | TK250-MAIN SHAFT BEARING ISSUES | SERVICING TO BE PLANNED | UMA MAHESH | 2024-05-31 | OPEN | INVESTIAGTION PLANNED
80 | HIGH | PROD | 2024-05-31 | TOOL LOCKING SOP(PRESS MACHINE) | SOP TO BE PREPARED | PARAM | 2024-05-31 | OPEN
81 | HIGH | MNT | 2024-05-31 | 164S-WIRE STARAIGHTNER ROLLERS | EN24 MATERIAL ROLLERS TO BE DELVELOPED FOR TEMPORARY PURPOSE | UMA MAHESH | 2024-06-14 | OPEN
82 | HIGH | MNT | 2024-05-31 | TRANSFORMER HEATING ISSUE | ROLLAR TIGHTESS V/S AMP V/S TEMP DATA TO B ESTABLISHED | UMA MAHESH/DILLI | 2024-05-31 | OPEN
83 | HIGH | HR | 2024-05-31 | FANS REQUIRED IN COLONY BUFFING AREA | TO BE PURCHASED AND DEPLOYED | HARI | 2024-05-31 | OPEN
84 | HIGH | NPD | 2024-06-04 | SUPRAJIT-OPEN ISSES TO BE RESOLVED | QA AND NPD TO TAKE THE CUSTOMER IN CONCALL AND EXPLAIN THE STANDARDS | SAMI/PARANDAMA | 2024-06-04 | OPEN
85 | HIGH | TOOL | 2024-06-05 | M5 X 12 PAN HEAD SCREW TOOL DAMAGE | POINTING ACTIVITY TO BE PROVED OUT TO START PRODUCTION | PARANDAMA | 2024-06-05 | OPEN
86 | HIGH | PUR/TOOL | 2024-06-05 | RDP ROLLING DIES LIFE IS GETTING MORE | FURTHER ORDER TO PRIORITIZE FOR RDP ONLY | RAJESH/PRANDAMA | 2024-06-05 | OPEN
87 | HIGH | PUR | 2024-06-05 | M16 X 1.5 ROLLING DIES | ORDERED 3 SET DIES NEED TO GET DELIVERED ON URGENT BASIS | RAJESH | 2024-06-17 | OPEN
88 | HIGH | MNT | 2024-06-07 | 6L4-FIRST STATION LENGTH ADJUSTMENT SCREW WORN OUT | TEMPORARY ACTION WELDING AND REWORK,PA-SPARES REQUIRED | UMA MAHESH | 2024-06-07 | OPEN
89 | HIGH | PROD | 2024-06-07 | MTR-30 WORK REST NEED TO INCREASE THE HEIGHT | WORK REST TO BE RODER M16 TO M27 | UMA MAHESH | 2024-06-07 | OPEN
90 | HIGH | PPC | 2024-06-07 | DH BOLT TRD PROCESS MISS AT BOLTON'S | INTERNAL SYSTEM AT PLANT TO BE REVIEWED FOR COUNTER MEASURES | DILLI/BRIJESH | 2024-06-08 | OPEN
91 | HIGH | PUR | 2024-06-07 | HAND TROLLEY ORDER STATUS | PURCHASE TO UPDATE | RAJESH | 2024-06-08 | OPEN
92 | HIGH | MNT | 2024-06-07 | CUSTOMIZED TROLLEYS( EXISTING HAND PALLETS LIFE ISSUE) | ONE SAMPLE TROLLEY TO BE MADE FOR MATERIAL MOVEMENT | UMA MAHESH | 2024-06-22 | OPEN
93 | HIGH | TOOL | 2024-06-12 | M8 X 14 SCHS 2ND AND 3RD STAGE CLEARENCE IS MORE | 2ND AND 3RD STATION DIE DESIGN MODIFICATION IS REQUIRED AND TO BE ORDERED | PARANDAM/RAJESH | 2024-07-31 | INDENT TO BE CLEARED ON 13-JUNE
94 | HIGH | MNT | 2024-06-12 | M8 WIRE STARIGHTNER ROLLERS | ROLLERS TO BE ORDERED-SS AND MS SEPARTE SETS | UMA MAHESH | 2024-06-19 | OPEN
95 | HIGH | TOOL | 2024-06-12 | JY TRIMMING DIE REQUIRED | ORDERED 30 NO'S YET TO RECEIVE | RAJESH | 2024-06-17 | 11 nos received
96 | HIGH | TOOL | 2024-06-12 | TK250-FINGERS REQUIRED | FINGERS-INDENT AND DRAWING REQUIRED | PARANDAMAN | 2024-06-13 | OPEN
97 | HIGH | TOOL | 2024-06-12 | TK250-FINGERS REQUIRED | ONCE DRAWINGS RECEIVED ORDERS WILL BE DONE | RAJESH | 2024-06-13 | OPEN
98 | HIGH | MNT | 2024-06-13 | 6L4-4TH STATION AMOUNT OF OPENING ROLLER ISSUE | REPLACE NEW ROLLER AND KAIZEN IS REQUIRED | DILLI/PARANDAMA/MAHESH | 2024-06-14 | OPEN
99 | HIGH | HR | 2024-06-15 | NIGHT SHIFT SECURITY PLAN ASSESEMENT | CHECK LIST TO PREPARED | HARI | 2024-06-17 | OPEN
100 | HIGH | PUR | 2024-06-15 | RM JUNE ORDER-HT FIRST | RM TO BE RECEIVED | RAJESH | 2024-06-23 | OPEN
101 | HIGH | MNT | 2024-06-15 | 84S 4TH STATION BUSH REQUIRED | SERVICABLE AND NEW ONE(5 NO'S) TO BE ORDERED | MAHESH/DILLI/PARANDAMA | 2024-06-17 | OPEN
102 | HIGH | TOOL | 2024-06-15 | KNURLING DIES M6 | DIES TO BE ORDERED AND RECEIVED | PARANDAMA | 2024-06-17 | OPEN
103 | HIGH | TOOL | 2024-06-17 | TOOL PRE-QUALIFICATION | PLAN AND ACTIVITIES TO BE INITIATED AT THE TOOL ROOM | PARANDAMA | 2024-06-20 | OPEN
104 | HIGH | MNT | 2024-06-17 | 164S-3RD STN SPINDLE BROKEN ISSUE | NEW ORDER WITH IMPROVED HARDNESS TO BE PROCURED | MAHESH |  | OPEN
105 | HIGH | PPC | 2024-06-19 | 84S-FEEDING ROLLER CHANGE | FEEDING ROLLERS CHANGE TO INITIATED AND COMPLETED | MAHESH | 2024-06-19 | OPEN
106 | HIGH | PPC | 2024-06-19 | 164S- CAM ROLLER 4TH STN MORE WEAR | NEED TO TAKE RE-SERVICE | MAHESH | 2024-06-19 | OPEN
107 | HIGH | MNT | 2024-06-19 | TRACK PLATE SPARE NOT AVILABLE | NEED TO ORDER-2 NO'S AND ORGANIZE | MAHESH | 2024-06-27 | OPEN
108 | HIGH | PPC | 2024-06-19 | M8-RM DEVIATION | M22/16 ROLLING PRODUCT DEVIATION REPORT | DILLI | 2024-06-19 | OPEN
109 | HIGH | MNT | 2024-06-24 | TK250-HORIZONTAL AND VERTICAL MOVING SLIDE PLAY AVAILBLE | MOVING SLIDE PLAY TO BE ADJUSTED | MAHESH/DILLI | 2024-06-24 | OPEN
110 | HIGH | MNT | 2024-06-24 | TK250-HORIZONTAL AND VERTICAL MOVING SLIDE PLAY AVAILBLE | ROOT CAUSE FOR PERMANENT ACTIONS | DILLI/PARANDAMAN | 2024-06-24 | OPEN
111 | HIGH | PPC | 2024-06-24 | PUSHER PLATE NOT AVILABLE | PUSHER PLATE NEED TO ORDER | MAHESH | 2024-06-24 | OPEN
112 | HIGH | MNT | 2024-06-24 | 164S/6L4-SHORT FEED SENSORS NOT AVAILBLE | SENSORS TO BE INSTALLED | MAHESH | 2024-06-24 | DISCUSS WITH SUPPLIER AND REVERT ON THE LEAD TIME
113 | HIGH | PUR | 2024-06-25 | 164S-FEED ROLLER SCORING HAPPENING | 10.65 FEED ROLLERS TO BE CONVERTED TO 13.60 | RAJESH |  | OPEN
114 | HIGH | TR/PROD | 2024-06-27 | 64S-M6 SHCS AND HS-A270 TOOL CONVERSTION | BEFORE USE REVIEW THE TOOL FOR EXPECTED TOOL LIFE | PARANDAMA/DILLI | 2024-06-27 | OPEN
115 | HIGH | MNT | 2024-06-29 | 64S BRAKE LINER ISSUE | SERIVCE ACTIVITY PLAN FOR THE COMING 7TH AND 8TH | MAHESH | 2024-07-07 | OPEN
116 | HIGH | TOOL | 2024-07-01 | KO PINS FOR M12 NOT AVAILABLE | CONVERTING M14 KO PINS DUE TO SHORTAGE OF M12 KO PINS | PARANDAMA/DILLI | 2024-07-01 | OPEN
117 | HIGH | TR/PROD | 2024-07-01 | M6X1X30 SHCS LENGTH OVER SIZE | DEVIATION NOTE BE RAISED, AWAITING TOOLS | PARANDAMA/DILLI | 2024-07-01 | OPEN
118 | HIGH | TR/PUR | 2024-07-02 | TK 250 TRANSFER FINGER REQUIRED | TRANSFER FINGERS TO BE ORDERED & RECEIVED (LEAD TIME 30 DAYS) | PARANDAMA/RAJESH | 2024-07-31 | OPEN
119 | HIGH | PROD | 2024-07-02 | 84S-DD BOLT DELAYED DUE TO 4TH STN FINGER SETTING | COUNTER MEASURE TO REPORTED FOR DELAYED SETTING | DILLI | 2024-07-03 | OPEN

## APRIL 26
S.NO | PRIORITY | DEPT | DATE | (MOM) PROBLEM DESCRIPTION | ACTION | RESP | EMAIL | TARGET | STATUS | REMARKS
1 | HIGH | PPC | 2026-04-20 | BAL -21PARTS DISPATCH COMMITMENT |  | DILLI | dilli.d@precifast.in | 2026-04-20 | OPEN
2 | HIGH | PPC | 2026-04-20 | MARCH'26 - AUTO SECTOR DISPATCH COMMITMENT |  | DILLI | dilli.d@precifast.in | 2026-04-20 | OPEN
3 | HIGH | MNT | 2026-04-20 | 164S MNT PLAN ACTIVES TIMING PLAN & SPARES | TO BE PREPARED AND CIRCULATE | UMA MAHESH | maintenance@precifast.in | 2026-04-20 | OPEN
4 | HIGH | HT/PUR | 2026-04-20 | MICRO STRUCTURE CHECKING |  | UMA MAHESH/RAJESH | maintenance@precifast.in / e.rajesh@precifast.in | 2026-04-20 | OPEN
5 | HIGH | PUR/PPC | 2026-04-20 | M/S TIVOLT PLATING MATL TO BE DISPATCH FROM - SUPPLIER END | TO BE ENSURE | DILLI/RAJESH | dilli.d@precifast.in / e.rajesh@precifast.in | 2026-04-20 | OPEN
6 | HIGH | QA | 2026-04-20 | M/S BEML DISPATCH |  | QA-BALA | sqa@precifast.in | 2026-04-20 | OPEN
7 | HIGH | TR/PROD | 2026-04-20 | INCH SERIES TOOLS CHECK UP(3/8:1-1/2,UNC& UNF) |  | RAJESH | e.rajesh@precifast.in | 2026-04-21 | OPEN
8 | HIGH | PUR | 2026-04-20 | M21 BACK FILLIER DIE REWORK | TO BE ARRANGE BACK AFTER REWORK TODAY | RAJESH/TRIPATHI | e.rajesh@precifast.in / ^prod@precifast.in | 2026-04-21 | OPEN
9 | HIGH | QA | 2026-04-20 | M/S TECH AUTO- SUPPLIER END | TO BE COMPLETED BY TODAY FOR ONE BILL | QA-BALA | sqa@precifast.in | 2026-04-20 | OPEN
10 | HIGH | PUR | 2026-04-20 | M5 X9 TORX PIN YET RECEIVE |  | RAJESH | e.rajesh@precifast.in | 2026-04-24 | OPEN
11 | HIGH | TR/PROD | 2026-04-20 | M5X21 TRAP DIE DRAWING REQD |  | DESIGN/NPD | parandama@precifast.in | _ | OPEN
12 | HIGH | STORE | 2026-04-20 | DEALER DISPATCH FOR KRIPA, VRASON, MECH MOTOR, BARTH MINING, SKAD |  | BALA | balakrishna.b@gmail.com |  | OPEN
13 | HIGH | PUR | 2026-04-20 | M20 X2.5 RE THREAD DIE TO BE DISPATCH FROM HYD |  | RAJESH | e.rajesh@precifast.in | 2026-04-21 | OPEN
14 | HIGH | PUR | 2026-04-20 | M16 JY TRIM DIE 1.5 DIE FROM HYD 2.10 TRIM DIE FROM NAHARS | 1.TO BE ARRANGE FROM HYD TODAY 2.ARRANGE BY 26/04/2026 | RAJESH | e.rajesh@precifast.in | 2026-04-26 | OPEN
15 | HIGH | PROD | 2026-04-20 | LBU236,PAN HEAD ,M12 SERIES, M21 SERIES , 1. LBU236 SUPPORT BY DILLI | TO BE FORGED AND MOVE TO NEXT OPNS | MANOHAR | prod@precifast.in | 2026-04-21 | OPEN
16 | HIGH | MKT | 2026-04-20 | M/S TECHNO CRAFT DISPATCH | TO BE CONFORMIED | BALA | balakrishna.b@gmail.com | 2026-04-20 | OPEN
17 | HIGH | PUR | 2026-04-20 | M12X1.75 EXTRUSION DIE | TO BE ARRANGE BACK AFTER REWORK TODAY | RAJESH/TRIPATHI | e.rajesh@precifast.in / prod@precifast.in | 2026-04-21 | OPEN
18 | HIGH | MKT | 2026-04-20 | ALL ORANGE INVOICES 32LACS | TO BE COMPLETED BEFORE 25TH APRIL | BALA | balakrishna.b@gmail.com | 2026-04-25 | OPEN
19 | HIGH | PPC | 2026-04-20 | M10X1.5X130 FB TIVOLT | ROLLING PROCESS TO BE COMPLETED | DILLI | dilli.d@precifast.in | 2026-04-21 | OPEN
20 | HIGH | MNT | 2026-04-20 | 6L4 TRANS UNIT REVIEW | MEETING TO BE SCHEDULED AT 22/04/2026@3.00PM TO 4.00 PM | DILLI | dilli.d@precifast.in | 2026-04-22 | OPEN
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
51
52
53
54

## TBF
S NO | Month | INVOICE NO | ORDER BOOKING NO | BOOKING DATE | CUSTOMER NAME | PRODUCT CODE | PRODUCT TYPE | SIZE | A/F | PITCH | LENGTH | GRADE | ORDER QTY | DISPATCH QTY | BALANCE QTY | LIST PRICE | ORDER VALUE | REMARKS | ITEM DESCRIPTION | DISPATCH DATE
1 | MAR | 3046/25-26 | 245252603006 | 2026-03-18 | MEGH MOTORS (GUWAHATI) | V010030204 | HHB | M10 | 17 | 1.5 | 30 | PPL-10.9 | 50000 | 0 | 50000 | 7.74 | 174150 | TBF | HHB M10X1.5X30 PPL-10.9 | 2025-05-10
2 | MAR | 3046/25-26 | 245252603006 | 2026-03-18 | MEGH MOTORS (GUWAHATI) | V010030202 | HHB | M10 | 16 | 1.5 | 30 | PPL-10.9 | 20000 | 0 | 20000 | 7.74 | 69660 | TBF | HHB M10X1.5X30 PPL-10.9 | 2025-05-10
3 | MAR | 2964/25-26 | 245252603008 | 2026-03-21 | KRIPA AUTO AGENCIES | L112025203 | HHS | M12 | 19 | 1.5 | 25 | PPL-10.9 | 600 | 0 | 600 | 12.91 | 3485.7 | TBF | HHS M12X1.5X25 PPL-10.9 | U/PACKING
4 | MAR | 3015/25-26 | 245252603011 | 2026-03-23 | SHREE KATEELESHWARI AUTO DISTRIBUTORS | L006070202 | HHB | M6 | 10 | 1 | 70 | PPL-10.9 | 800 | 0 | 800 | 6.27 | 2257.2 | TBF | HHB M6X1X70 PPL-10.9 | 2025-05-10
5 | MAR | 3015/25-26 | 245252603011 | 2026-03-23 | SHREE KATEELESHWARI AUTO DISTRIBUTORS | L008025201 | HHS | M8 | 13 | 1.25 | 25 | PPL-10.9 | 1600 | 0 | 1600 | 4.89 | 3520.8 | TBF | HHS M8X1.25X25 PPL-10.9 | 2025-05-10
6 | MAR | 3015/25-26 | 245252603011 | 2026-03-23 | SHREE KATEELESHWARI AUTO DISTRIBUTORS | L112025203 | HHS | M12 | 19 | 1.5 | 25 | PPL-10.9 | 600 | 0 | 600 | 12.91 | 3485.7 | TBF | HHS M12X1.5X25 PPL-10.9 | U/PACKING
7 | MAR | 3015/25-26 | 245252603011 | 2026-03-23 | SHREE KATEELESHWARI AUTO DISTRIBUTORS | L112035203 | HHS | M12 | 19 | 1.5 | 35 | PPL-10.9 | 400 | 0 | 400 | 16.26 | 2926.8 | TBF | HHS M12X1.5X35 PPL-10.9 | U/PACKING
8 | MAR | 3015/25-26 | 245252603011 | 2026-03-23 | SHREE KATEELESHWARI AUTO DISTRIBUTORS | L112040203 | HHS | M12 | 19 | 1.5 | 40 | PPL-10.9 | 400 | 0 | 400 | 13.06 | 2350.8 | TBF | HHS M12X1.5X40 PPL-10.9 | U/PACKING
9 | MAR | 3015/25-26 | 245252603011 | 2026-03-23 | SHREE KATEELESHWARI AUTO DISTRIBUTORS | L014050203 | HHS | M14 | 22 | 2 | 50 | PPL-10.9 | 240 | 0 | 240 | 24.86 | 2684.88 | TBF | HHS M14X2X50 PPL-10.9 | 2026-05-25
10 | MAR | 3015/25-26 | 245252603011 | 2026-03-23 | SHREE KATEELESHWARI AUTO DISTRIBUTORS | L016150202 | HHB | M16 | 24 | 2 | 150 | PPL-10.9 | 120 | 0 | 120 | 89.9 | 4854.6 | TBF | HHB M16X2X150 PPL-10.9 | 2026-05-10
11 | MAR | 3015/25-26 | 245252603011 | 2026-03-23 | SHREE KATEELESHWARI AUTO DISTRIBUTORS | L018100202 | HHB | M18 | 27 | 2.5 | 100 | PPL-10.9 | 160 | 0 | 160 | 80.06 | 5764.32 | TBF | HHB M18X2.5X100 PPL-10.9 | awaiting r.m
12 | MAR | 2979/25-26 | 245252603006 | 2026-03-18 | MEGH MOTORS (GUWAHATI) | L008105202 | HHB | M8 | 13 | 1.25 | 105 | PPL-10.9 | 400 |  | 400 | 15.34 | 2761.2 | TBF | HHB M8X1.25X105 PPL-10.9 | npd
13 | MAR | 2979/25-26 | 245252603006 | 2026-03-18 | MEGH MOTORS (GUWAHATI) | L008110202 | HHB | M8 | 13 | 1.25 | 110 | PPL-10.9 | 300 |  | 300 | 16.12 | 2176.2 | TBF | HHB M8X1.25X110 PPL-10.9 | npd
14 | MAR | 2979/25-26 | 245252603006 | 2026-03-18 | MEGH MOTORS (GUWAHATI) | L008125202 | HHB | M8 | 13 | 1.25 | 125 | PPL-10.9 | 300 |  | 300 | 19.58 | 2643.3 | TBF | HHB M8X1.25X125 PPL-10.9 | npd
15 | MAR | 2979/25-26 | 245252603006 | 2026-03-18 | MEGH MOTORS (GUWAHATI) | L010080204 | HHB | M10 | 17 | 1.5 | 80 | PPL-10.9 | 320 |  | 320 | 20.07 | 2890.08 | TBF | HHB M10X1.5X80 PPL-10.9 | 2026-05-18
16 | MAR | 2979/25-26 | 245252603006 | 2026-03-18 | MEGH MOTORS (GUWAHATI) | L010090204 | HHB | M10 | 17 | 1.5 | 90 | PPL-10.9 | 960 |  | 960 | 22.3 | 9633.6 | TBF | HHB M10X1.5X90 PPL-10.9 | 2026-05-18
17 | MAR | 2979/25-26 | 245252603006 | 2026-03-18 | MEGH MOTORS (GUWAHATI) | L010100204 | HHB | M10 | 17 | 1.5 | 100 | PPL-10.9 | 840 |  | 840 | 24.39 | 9219.42 | TBF | HHB M10X1.5X100 PPL-10.9 | 2026-05-18
18 | MAR | 2979/25-26 | 245252603006 | 2026-03-18 | MEGH MOTORS (GUWAHATI) | L010125204 | HHB | M10 | 17 | 1.5 | 125 | PPL-10.9 | 200 |  | 200 | 29.85 | 2686.5 | TBF | HHB M10X1.5X125 PPL-10.9 | 2026-05-18
19 | MAR | 2967/25-26 | 245252603006 | 2026-03-18 | MEGH MOTORS (GUWAHATI) | L112025203 | HHS | M12 | 19 | 1.5 | 25 | PPL-10.9 | 1200 |  | 1200 | 12.91 | 6971.4 | TBF | HHS M12X1.5X25 PPL-10.9 | U/PACKING
20 | MAR | 2967/25-26 | 245252603006 | 2026-03-18 | MEGH MOTORS (GUWAHATI) | L112035203 | HHS | M12 | 19 | 1.5 | 35 | PPL-10.9 | 2000 |  | 2000 | 16.26 | 14634 | TBF | HHS M12X1.5X35 PPL-10.9 | U/PACKING
21 | MAR | 2967/25-26 | 245252603006 | 2026-03-18 | MEGH MOTORS (GUWAHATI) | L112040203 | HHS | M12 | 19 | 1.5 | 40 | PPL-10.9 | 800 |  | 800 | 13.06 | 4701.6 | TBF | HHS M12X1.5X40 PPL-10.9 | U/PACKING
22 | MAR | 2967/25-26 | 245252603006 | 2026-03-18 | MEGH MOTORS (GUWAHATI) | L112045203 | HHS | M12 | 19 | 1.5 | 45 | PPL-10.9 | 800 |  | 800 | 18.46 | 6645.6 | TBF | HHS M12X1.5X45 PPL-10.9 | U/PACKING
23 | MAR | 2967/25-26 | 245252603006 | 2026-03-18 | MEGH MOTORS (GUWAHATI) | L112050203 | HHS | M12 | 19 | 1.5 | 80 | PPL-10.9 | 800 |  | 800 | 18.99 | 6836.4 | TBF | HHS M12X1.5X80 PPL-10.9 | 2026-05-10
24 | MAR | 2967/25-26 | 245252603006 | 2026-03-18 | MEGH MOTORS (GUWAHATI) | L112065204 | HHB | M12 | 19 | 1.5 | 65 | PPL-10.9 | 240 |  | 240 | 25.01 | 2701.08 | TBF | HHB M12X1.5X65 PPL-10.9 | 2026-05-18
25 | MAR | 2967/25-26 | 245252603006 | 2026-03-18 | MEGH MOTORS (GUWAHATI) | L112100204 | HHB | M12 | 19 | 1.5 | 100 | PPL-10.9 | 200 |  | 200 | 35.06 | 3155.4 | TBF | HHB M12X1.5X100 PPL-10.9 | 2026-05-18
26 | MAR | 2967/25-26 | 245252603006 | 2026-03-18 | MEGH MOTORS (GUWAHATI) | L112125204 | HHB | M12 | 19 | 1.5 | 125 | PPL-10.9 | 320 |  | 320 | 44.91 | 6467.04 | TBF | HHB M12X1.5X125 PPL-10.9 | 2026-05-18
27 | MAR | 2967/25-26 | 245252603006 | 2026-03-18 | MEGH MOTORS (GUWAHATI) | L112130204 | HHB | M12 | 19 | 1.5 | 130 | PPL-10.9 | 160 |  | 160 | 45.08 | 3245.76 | TBF | HHB M12X1.5X130 PPL-10.9 | 2026-05-18
28 | MAR | 2967/25-26 | 245252603006 | 2026-03-18 | MEGH MOTORS (GUWAHATI) | L012065203 | HHS | M12 | 19 | 1.75 | 65 | PPL-10.9 | 640 |  | 640 | 25.01 | 7202.88 | TBF | HHS M12X1.75X65 PPL-10.9 | DIE NOT AVL
29 | MAR | 2967/25-26 | 245252603006 | 2026-03-18 | MEGH MOTORS (GUWAHATI) | L114055204 | HHB | M14 | 22 | 1.5 | 55 | PPL-10.9 | 240 |  | 240 | 30.8 | 3326.4 | TBF | HHB M14X1.5X55 PPL-10.9 | 2026-05-25
30 | MAR | 2967/25-26 | 245252603006 | 2026-03-18 | MEGH MOTORS (GUWAHATI) | L114150204 | HHB | M14 | 22 | 1.5 | 150 | PPL-10.9 | 60 |  | 60 | 67.88 | 1832.76 | TBF | HHB M14X1.5X150 PPL-10.9 | 2026-05-25
31 | MAR | 2967/25-26 | 245252603006 | 2026-03-18 | MEGH MOTORS (GUWAHATI) | L014075203 | HHS | M14 | 22 | 2 | 75 | PPL-10.9 | 200 |  | 200 | 39.56 | 3560.4 | TBF | HHS M14X2X75 PPL-10.9 | 2026-05-25
32 | MAR | 2967/25-26 | 245252603006 | 2026-03-18 | MEGH MOTORS (GUWAHATI) | L016050201 | HHS | M16 | 24 | 2 | 50 | PPL-10.9 | 400 |  | 400 | 37.16 | 6688.8 | TBF | HHS M16X2X50 PPL-10.9
33 | MAR | 3016/25-26 | 245252603010 | 2026-03-31 | SHUBAM TRADERS | V012035204 | HHB | M12(19A/F) | 19 | 1.75 | 35 | PPL-10.9 | 20000 |  | 20000 | 5.25 | 105000 | TBF | HHB M12(19A/F)X1.75X35 PPL-10.9
34 | MAR | 3012/25-26 | 245252603010 | 2026-03-23 | SHUBAM TRADERS | L112065204 | HHB | M12 | 19 | 1.5 | 65 | PPL-10.9 | 640 |  | 640 | 25.01 | 7202.88 | TBF | HHB M12X1.5X65 PPL-10.9 | 2026-05-18
35 | MAR | 3012/25-26 | 245252603010 | 2026-03-23 | SHUBAM TRADERS | L012020203 | HHS | M12 | 19 | 1.75 | 20 | PPL-10.9 | 400 |  | 400 | 11.61 | 2089.8 | TBF | HHS M12X1.75X20 PPL-10.9 | 2026-05-18
36 | MAR | 3012/25-26 | 245252603010 | 2026-03-23 | SHUBAM TRADERS | L012030203 | HHS | M12 | 19 | 1.75 | 30 | PPL-10.9 | 1200 |  | 1200 | 14.43 | 7792.2 | TBF | HHS M12X1.75X30 PPL-10.9
37 | MAR | 3012/25-26 | 245252603010 | 2026-03-23 | SHUBAM TRADERS | L012085204 | HHB | M12 | 19 | 1.75 | 85 | PPL-10.9 | 120 |  | 120 | 31.11 | 1679.94 | TBF | HHB M12X1.75X85 PPL-10.9 | 2026-05-18
38 | MAR | 3012/25-26 | 245252603010 | 2026-03-23 | SHUBAM TRADERS | L114055204 | HHB | M14 | 22 | 1.5 | 55 | PPL-10.9 | 960 |  | 960 | 30.8 | 13305.6 | TBF | HHB M14X1.5X55 PPL-10.9 | 2026-05-25
39 | MAR | 3012/25-26 | 245252603010 | 2026-03-23 | SHUBAM TRADERS | L116055202 | HHB | M16 | 24 | 1.5 | 55 | PPL-10.9 | 200 |  | 200 | 40.85 | 3676.5 | TBF | HHB M16X1.5X55 PPL-10.9 | 2026-05-10
40 | MAR | 3012/25-26 | 245252603010 | 2026-03-23 | SHUBAM TRADERS | L532038602 | HHB | 3/8 | - | UNC | 1.5 | PPL-8.8 | 1600 |  | 1600 | 10.05 | 7236 | TBF | HHB 3/8XUNCX1.5 PPL-8.8 | 2026-05-10
41 | MAR | 3012/25-26 | 245252603010 | 2026-03-23 | SHUBAM TRADERS | L532038601 | HHS | 3/8 | - | UNC | 1.5 | PPL-8.8 | 800 |  | 800 | 10.05 | 3618 | TBF | HHS 3/8XUNCX1.5 PPL-8.8 | 2026-05-10
42 | MAR | 3012/25-26 | 245252603010 | 2026-03-23 | SHUBAM TRADERS | L632038602 | HHB | 3/8 | - | UNF | 1.5 | PPL-8.8 | 600 |  | 600 | 10.05 | 2713.5 | TBF | HHB 3/8XUNFX1.5 PPL-8.8 | 2026-05-10
43 | MAR | 3248/25-26 | 245252603018 | 2026-03-31 | SHUBAM TRADERS | L008080202 | HHB | M8 | 13 | 1.25 | 80 | PPL-10.9 | 600 |  | 600 | 12.05 | 3253.5 | TBF | HHB M8X1.25X80 PPL-10.9 | 2025-05-10
44 | MAR | 3248/25-26 | 245252603018 | 2026-03-31 | SHUBAM TRADERS | V010030204 | HHB | M10 | 17 | 1.5 | 30 | PPL-10.9 | 8000 |  | 8000 | 7.74 | 27864 | TBF | HHB M10X1.5X30 PPL-10.9 | 2025-05-10
45 | MAR | 3248/25-26 | 245252603018 | 2026-03-31 | SHUBAM TRADERS | L010090204 | HHB | M10 | 17 | 1.5 | 90 | PPL-10.9 | 1600 |  | 1600 | 22.3 | 16056 | TBF | HHB M10X1.5X90 PPL-10.9 | 2026-05-18
46 | MAR | 3248/25-26 | 245252603018 | 2026-03-31 | SHUBAM TRADERS | L010140204 | HHB | M10 | 17 | 1.5 | 140 | PPL-10.9 | 600 |  | 600 | 33.03 | 8918.1 | TBF | HHB M10X1.5X140 PPL-10.9 | 2026-05-18
47 | MAR | 3248/25-26 | 245252603018 | 2026-03-31 | SHUBAM TRADERS | L016090202 | HHB | M16 | 24 | 2 | 90 | PPL-10.9 | 120 |  | 120 | 59.73 | 3225.42 | TBF | HHB M16X2X90 PPL-10.9 | 2026-05-10
48 | MAR | 3248/25-26 | 245252603018 | 2026-03-31 | SHUBAM TRADERS | L016100202 | HHB | M16 | 24 | 2 | 100 | PPL-10.9 | 120 |  | 120 | 65.03 | 3511.62 | TBF | HHB M16X2X100 PPL-10.9 | 2026-05-10
49 | MAR | 3248/25-26 | 245252603018 | 2026-03-31 | SHUBAM TRADERS | L018055202 | HHB | M18 | 27 | 2.5 | 55 | PPL-10.9 | 160 |  | 160 | 51.18 | 3684.96 | TBF | HHB M18X2.5X55 PPL-10.9 | awaiting r.m
50 | MAR | 3248/25-26 | 245252603018 | 2026-03-31 | SHUBAM TRADERS | L018090202 | HHB | M18 | 27 | 2.5 | 90 | PPL-10.9 | 80 |  | 80 | 73.39 | 2642.04 | TBF | HHB M18X2.5X90 PPL-10.9 | awaiting r.m
51 | MAR | 3248/25-26 | 245252603018 | 2026-03-31 | SHUBAM TRADERS | L020050201 | HHS | M20 | 30 | 2.5 | 50 | PPL-10.9 | 360 |  | 360 | 62.68 | 10154.16 | TBF | HHS M20X2.5X50 PPL-10.9 | 2026-05-10
52 | MAR | 3248/25-26 | 245252603018 | 2026-03-31 | SHUBAM TRADERS | L020170202 | HHB | M20 | 30 | 2.5 | 170 | PPL-10.9 | 40 |  | 40 | 161.03 | 2898.54 | TBF | HHB M20X2.5X170 PPL-10.9 | die reqd
53 | MAR | 3248/25-26 | 245252603018 | 2026-03-31 | SHUBAM TRADERS | L020220202 | HHB | M20 | 30 | 2.5 | 220 | PPL-10.9 | 150 |  | 150 | 203.7 | 13749.75 | TBF | HHB M20X2.5X220 PPL-10.9 | die reqd
54 | MAR | 3248/25-26 | 245252603018 | 2026-03-31 | SHUBAM TRADERS | L020280202 | HHB | M20 | 30 | 2.5 | 280 | PPL-10.9 | 60 |  | 60 | 249.83 | 6745.41 | TBF | HHB M20X2.5X280 PPL-10.9 | die reqd
55 | MAR | 3248/25-26 | 245252603018 | 2026-03-31 | SHUBAM TRADERS | L022080202 | HHB | M22 | 34 | 2.5 | 80 | PPL-10.9 | 120 |  | 120 | 125.28 | 6765.12 | TBF | HHB M22X2.5X80 PPL-10.9 | awaiting r.m
56 | MAR | 3248/25-26 | 245252603018 | 2026-03-31 | SHUBAM TRADERS | L022100202 | HHB | M22 | 34 | 2.5 | 100 | PPL-10.9 | 120 |  | 120 | 147.52 | 7966.08 | TBF | HHB M22X2.5X100 PPL-10.9 | awaiting r.m
57 | MAR | 3248/25-26 | 245252603018 | 2026-03-31 | SHUBAM TRADERS | L024130202 | HHB | M24 | 36 | 3 | 130 | PPL-10.9 | 40 |  | 40 | 215.88 | 3885.84 | TBF | HHB M24X3X130 PPL-10.9 | 2026-05-10
58 | MAR | 3248/25-26 | 245252603018 | 2026-03-31 | SHUBAM TRADERS | L024160202 | HHB | M24 | 36 | 3 | 160 | PPL-10.9 | 30 |  | 30 | 255.68 | 3451.68 | TBF | HHB M24X3X160 PPL-10.9 | 2026-05-10
59 | MAR | 3248/25-26 | 245252603018 | 2026-03-31 | SHUBAM TRADERS | L024220202 | HHB | M24 | 36 | 3 | 220 | PPL-10.9 | 100 |  | 100 | 332.73 | 14972.85 | TBF | HHB M24X3X220 PPL-10.9 | 2026-05-10
60 | MAR | 3248/25-26 | 245252603018 | 2026-03-31 | SHUBAM TRADERS | L027200202 | HHB | M27 | 41 | 3 | 200 | PPL-10.9 | 25 |  | 25 | 408.04 | 4590.45 | TBF | HHB M27X3X200 PPL-10.9 | check & update
61 | MAR | 3248/25-26 | 245252603018 | 2026-03-31 | SHUBAM TRADERS | L532038602 | HHB | 3/8 | - | UNC | 1 1/2" | PPL-8 | 1600 |  | 1600 | 10.05 | 7236 | TBF | HHB 3/8XUNCX1 1/2" PPL-8 | 2026-05-10
62 | MAR | 3248/25-26 | 245252603018 | 2026-03-31 | SHUBAM TRADERS | G006012421 | FS | M6 | - | 1 | 12 | PPL-8.8 | 3200 |  | 3200 | 2.19 | 3153.6 | TBF | FS M6X1X12 PPL-8.8 | 2025-05-10
63 | MAR | 3248/25-26 | 245252603018 | 2026-03-31 | SHUBAM TRADERS | G008050421 | FS | M8 | - | 1.25 | 50 | PPL-8.8 | 600 |  | 600 | 8.13 | 2195.1 | TBF | FS M8X1.25X50 PPL-8.8 | 2025-05-10
64 | MAR | 3248/25-26 | 245252603018 | 2026-03-31 | SHUBAM TRADERS | G010040421 | FS | M10 | - | 1.5 | 40 | PPL-8.8 | 400 |  | 400 | 12.25 | 2205 | TBF | FS M10X1.5X40 PPL-8.8 | NPD
65 | MAR | 3248/25-26 | 245252603018 | 2026-03-31 | SHUBAM TRADERS | G010025421 | FS | M10 | - | 1.5 | 25 | PPL-8.8 | 600 |  | 600 | 9.67 | 2610.9 | TBF | FS M10X1.5X25 PPL-8.8 | NPD
66 | MAR | 3248/25-26 | 245252603018 | 2026-03-31 | SHUBAM TRADERS | G010035421 | FS | M10 | - | 1.5 | 35 | PPL-8.8 | 600 |  | 600 | 11.53 | 3113.1 | TBF | FS M10X1.5X35 PPL-8.8 | NPD
67 | MAR | 3248/25-26 | 245252603018 | 2026-03-31 | SHUBAM TRADERS | G116120222 | FB | M16 | - | 1.5 | 120 | PPL-10.9 | 80 |  | 80 | 81.06 | 2918.16 | TBF | FB M16X1.5X120 PPL-10.9 | npd
68 | MAR | 3248/25-26 | 245252603018 | 2026-03-31 | SHUBAM TRADERS | G016060202 | FB | M16 | - | 2 | 60 | PPL-10.9 | 480 |  | 480 | 51.12 | 11041.92 | TBF | FB M16X2X60 PPL-10.9 | npd
69 | MAR | 3248/25-26 | 245252603018 | 2026-03-31 | SHUBAM TRADERS | G016065202 | FB | M16 | - | 2 | 65 | PPL-10.9 | 480 |  | 480 | 53.62 | 11581.92 | TBF | FB M16X2X65 PPL-10.9 | npd
70 | MAR | 3248/25-26 | 245252603018 | 2026-03-31 | SHUBAM TRADERS | G016070202 | FB | M16 | - | 2 | 70 | PPL-10.9 | 240 |  | 240 | 56.12 | 6060.96 | TBF | FB M16X2X70 PPL-10.9 | npd
71 | MAR | 3248/25-26 | 245252603018 | 2026-03-31 | SHUBAM TRADERS | G016075202 | FB | M16 | - | 2 | 75 | PPL-10.9 | 600 |  | 600 | 58.6 | 15822 | TBF | FB M16X2X75 PPL-10.9 | npd

## Sheet4
Sl no | Part Number | Description | Schedule Qty | Dispatch date from plant | 4M Related
1 | DK902626 | M6x1x10 HHS -A270 | 21,402 | 2026-04-27 | ok
2 | LAC00198 | M6X1X25 SHCS-A800 | 6,767 | 2026-04-28 | ok
3 | JZ181206 | PHS M5X21-A270 | 15,219 |  | Trap die required
4 | KAEA0616 | SPL M6X1X16-4.8 | 5,280 | 2026-04-26 | ok
5 | LHA00001 | M6X17.5 PIN | 900 | 31-04-2026 | CRITICAL
6 | KADA0612 | FL M6X1X12 -4.8 | 45,800 | 2024-04-23 | 1010 RM req /rm deviation
7 | KAED0610 | SPL M6X1X10-8.8 | 2,050 | 2026-04-26 | including 4 days HT outsourcing
8 | KAED0622 | SPL M6X1X22-8.8 | 5,020 | 2026-04-26 | including 4 days HT outsourcing
9 | KBUA0614 | PHSM6X14 | 12,410 |  | BO
10 | KAAA0514 | HHS M5X14-4.8 | 11,850 | 2026-04-25 | ok
11 | KADD0620 | FL M6X1X20-8.8 | 6,900 | 2026-04-28 | including 4 days HT outsourcing
12 | LBU00273 | SSB M6X9-A270 | 4,080 | 2026-04-21 | ok
13 | LBU00236 | SSBM8X39.3-A800 | 16,425 | 31-04-2026 | up to month end dispatch
14 | KADA0614 | FL M6X1X14-4.8 | 10,000 | 2026-06-25 | 1010 RM req /rm deviation
15 | KBUA0614 | PHSM6X14 | 12,410 |  | BO
16 | KAAA0514 | HHS M5X14-4.8 | 11,850 | 2026-04-26 | 1010 RM req /rm deviation
17 | KAAA0525 | HHS M5X25-4.8 | 50,000 | 2026-04-27 | 1010 RM req /rm deviation
18 | KAAA0825 | HHS M8X25-4.8 | 7,000 |  | Rm red
19 | KADD0620 | FL M6X1X20-8.8 | 6,900 | 2026-04-28 | including 4 days HT outsourcing
20 | KADD0630 | FL M6X1X20-8.8 | 10,000 | 2026-04-28 | including 4 days HT outsourcing
21 | KACF0516 | SSB M6X9-A270 | 283134 |  | Top nip issue